## COEM_Package_20200302
No | Package | Type | Project | ComponentName | TaskID | ItemName | Type of Comment | BB | Database | ItemRevision | Owner Contact | Task Jira | TaskGroup | Tester | PeerReviewer | Status Review | ELOC Assigned | ELOC Recheck With Tool | LOC Complete | Estimation base TOOL | Actual hour | Status | Planned Start | Planned End | Start | End | Status Result | C0 | C1 | MCDC | Reason | Remark
1 | 20200302 | PSW | GAC_220680_Carbon_A18_ESPHevx_FPA/RPA_BL03 | rb\as\gaig\prj\dsmpr\src\RBVoltageHandler\src | 1348323 | RBVoltageHandler_Suppression.c | Auto | - | GAC_ESPHevX_HADHAP_Int | - | CHEN Xiaomin (CC-AS/EVA-SW31-CN) |  | T01 | duong.nguyen | hieu.nguyen-trung | Yes | 113 | 113 | 113 | 3 | 4 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-03 | OK | 100 | 100 | 100
2 | 20200302 | PSW | MC_227282_SGMW_E200_Plus_ESPCPiGen9.3_BSS04_SP02 | rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src | 1345876 | SGMW_RBA_NDS_HBCRequest_Callout.c | Auto | bb99885 | SGMW_ESP93_Carbon_Int | - | WANG Yang (CC-AS/EVA-SW32-CN) |  | T01 | loc.do-phu | hieu.nguyen-trung | Yes | 148 | 357 | 357 | 10 | 6 | Ready for review | 2020-03-03 | 2020-03-04 | 2020-03-02 | 2020-03-02 | OK | 100 | 100 | 100 | Tool collect 148 ELOC, but the real is 357
3 | 20200302 | PSW | 241595_GAC_A27_ESP9.3CP_BL04 | rb\as\gaig\A10\dsmpr\src\RBHMI\src | 1350941 | RBHMI_LDMLamp_CNMS.c | Auto | BB81650 & BB81651 | Gac_ESP93CP_A26HD_Int | - | MIAO Huafeng (CC-AS/EVA-SW32-CN) |  | T01 | duong.nguyen | hieu.nguyen-trung | Yes | 291 | 291 | 291 | 8 | 10 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-03 | OK | 100 | 100 | 100 | Wrong extension C "RBHMI_LDMLamp_CNMS.C" | Got 1 findings
4 | 20200302 | PSW | 223331_GAC_A39_Carbon_ESP9.3HD_OBD_BL07 | rb\as\cnms_core\app\obd\ObdCyclesHandler\src | 1351929 | ObdCyclesHandler.c | Auto | bb99735 | GAC_ESP93CP_Carbon_Int | - | CHEN Xiaomin (CC-AS/EVA-SW31-CN) |  | T01 | chung.ly | hieu.nguyen-trung | Yes | 254 | 254 | 254 | 4.51 | 10 | Pending for OPL | 2020-03-02 | 2020-03-03 | 2020-03-02 | 2020-03-03 | NG | 100 | 100 | 95 | Bug (Condition is always TRUE) so can not cover MCDC. | Got 1 defect Reason: not send to internal team
5 | 20200302 | ASW | DFN_ESP_Gen9.3_532EC_244112_BSS01 | - | 1352219 | PAP_Odometry | Auto | - | 1352219 | V4.2.104.1 | QIAN Li (CC-AS/EVA-SW2-CN) |  | T01 | thanh.nguyen-kim | hieu.nguyen-trung | Yes | 19 | 19 | 19 | 1.16 | 4 | Pending for OPL | 2020-03-02 | 2020-03-03 | 2020-03-03 | 2020-03-03 | NG | 95.6 | 96 | - | Bug (Condition is always TRUE) | Got 1 findings
6 | 20200302 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1351848 | RBAPLCUST_EOLDelayCtrlOrAPBMi.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | SUN Yun (CC-AS/EVA-SW31-CN) |  | T02 | thanh.nguyen-kim | hieu.nguyen-trung | Yes | 478 | 478 | 478 | 8.49 | 14 | Ready for PLC | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-04 | NG | 99 | 99 | 100 | Bug (Condition not occur) | Got 1 findings
7 | 20200302 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | rb\as\sgmw\core\app\dcom\RBAPLCust\src\ESP | 1351848 | RBAPLCUST_RDBI_TPMS.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | SUN Yun (CC-AS/EVA-SW31-CN) |  | T02 | loc.do-phu | hieu.nguyen-trung | Yes | 286 | 286 | 286 | 5.08 | 1 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-03 | 2020-03-02 | OK | 100 | 100 | 100
8 | 20200302 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | rb\as\sgmw\core\app\dcom\RBAPLCust\src\ESP | 1351848 | RBAPLCUST_RoutineControl_TPMSReset.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | SUN Yun (CC-AS/EVA-SW31-CN) |  | T02 | chung.ly | hieu.nguyen-trung | Yes | 110 | 110 | 110 | 1.95 | 4 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100
9 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\gaig\A10\app\net\RBScl\RBSclGAC\src | 1278532 | RB_SCL_GAC_RX.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS/EVA-SW31-CN) |  | T03 | loc.do-phu | hieu.nguyen-trung | Yes | 251 | 294 | 294 | 5.22 | 6.5 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-03 | 2020-03-03 | OK | 100 | 100 | 100 | Actually ELOC = 294
10 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\gaig\A10\app\net\RBScl\RBSclGAC\src | 1278532 | RB_SCL_GAC_TX.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS/EVA-SW31-CN) |  | T03 | loc.do-phu | hieu.nguyen-trung | Yes | 101 | 101 | 101 | 1.79 | 1.5 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100
11 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\cnms_core\app\net\scl\LDMFunctions\ACC\src | 1278532 | NET_SCL_Tx_AEB.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS/EVA-SW31-CN) |  | T03 | duong.nguyen |  |  | 90 | 90 | 90 | 1.6 | 2 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | NG | 86 | 83 | 100
12 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\cnms_core\app\net\scl\LDMFunctions\APA\src | 1278532 | NET_SCL_Tx_APAInformSts.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS/EVA-SW31-CN) |  | T03 | loc.do-phu | hieu.nguyen-trung | Yes | 101 | 183 | 183 | 3.25 | 3 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100 | Actually ELOC = 183
13 | 20200303 | PSW | BYD_IPB_SW_Mainstream_BL05 | rb\as\BYD\ipb\app\net\RBScl\Scl_Callout\src | 1352115 | RBA_NDS_Complex_Callout.c | Auto | none | BYD_IPB_BL05_Int | - | GUO Sasa (CC-AS/EVA-SW3-CN) |  | T01 | chung.ly |  |  | 828 | 828 |  | 14.72 | 16 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-04 | 2020-03-06 | NG | 100 | 100 | 98 | Bug (Condition is always TRUE)
14 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\dcom\RBAPLCust\src | 1353313 | RBAPLCUST_RBDI_NVMData.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH/EAS12) |  | T01 | loc.do-phu |  |  | 371 | 371 | 371 | 6.59 | 3 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100 | OPL It does not impact to SW functionality.
15 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\dcom\RBAPLCust\src | 1353313 | RBAPLCUST_RDBI_PBCData.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH/EAS12) |  | T01 | loc.do-phu |  |  | 254 | 254 | 254 | 4.51 | 2 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
16 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\net\scl\Callout\src\ATMwithoutSportPlus | 1353313 | NET_ATM_Callout_GWM.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH/EAS12) |  | T01 | thanh.nguyen-kim |  |  | 395 | 395 | 395 | 7.02 | 2 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
17 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\net\scl\Callout\src\ATMwithSportPlus | 1353313 | NET_ATM_Callout_GWM.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH/EAS12) |  | T01 | thanh.nguyen-kim |  |  | 395 | 395 | 395 | 7.02 | 3 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
18 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_ABS_3_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | duong.nguyen | duong.nguyen | Yes | 96 | 96 | 96 | 1.7 | 1.5 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | NG | 97 | 95 | 92 | OPL is already feedback, confirm it can be ignore
19 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_APC_1_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | loc.do-phu | duong.nguyen | Yes | 28 | 28 | 28 | 0.49 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
20 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_ESP_3_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | loc.do-phu | duong.nguyen | Yes | 36 | 36 | 36 | 0.64 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
21 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_HCU_PT_10_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | chung.ly | duong.nguyen | Yes | 80 | 80 | 80 | 1.42 | 2 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | NG | 100 | 100 | 75 | Bug, con not cover MCDC beacause this is true case for above condition
22 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_HCU_PT_2_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | loc.do-phu | duong.nguyen | Yes | 33 | 33 | 33 | 0.58 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
23 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_SystemInfo.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | thanh.nguyen-kim | duong.nguyen | Yes | 212 | 212 | 212 | 3.76 | 2 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
24 | 20200303 | ASW | - | - | 1353762 | HDC_InvalidThrPos | Auto | - | 1353762 | V3.3.147305.2 | Nguyen Quang Vinh (RBVH/EAS15) |  |  | duong.nguyen |  |  | 50 | 50 | 50 | 3.07 | 3 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-06 |  |  |  |  | Have issues with database, complexity of code
25 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | 1341660 | RBAPLCUST_RDBI_AnalogData.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | duong.nguyen |  |  | 77 | 77 | 77 | 1.36 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
26 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | 1341660 | RBAPLCUST_RDBI_StatusInformation.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | duong.nguyen |  |  | 44 | 44 | 44 | 0.78 | 1 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
27 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | 1341660 | RBAPLCUST_RoutineControl_iBoosterActuatorTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | duong.nguyen |  |  | 210 | 210 | 210 | 3.73 | 2 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100 | No code
28 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_InputOutputControl.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | duong.nguyen |  |  | 622 | 622 | 622 | 11.05 | 8 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100 | -
29 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_InputOutputControl_GeneralFunctions.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 97 | 97 |  | 1.72 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
30 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_ActuationState.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 100 | 100 |  | 1.77 | 0.75 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
31 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_CBDS.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 8 | 8 |  | 0.14 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 |  | - | - | - | No code, already confirmed with Mr.Hai
32 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_IOCtrlState.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 148 | 148 |  | 2.63 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
33 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_IPBAssemblyMode.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 17 | 17 | 17 | 0.3 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
34 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_PBC.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 18 | 18 | 18 | 0.32 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
35 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_SystemData.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | loc.do-phu |  |  | 129 | 129 | 129 | 2.29 | 3 | Ready for delivery |  | 2020-03-11 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100 |  | Fixed comment
36 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_SystemSensor.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | loc.do-phu |  |  | 164 | 196 | 196 | 3.48 | 4 | Ready for review |  | 2020-03-11 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100 |  | Fixed comment, function switch. Re-run OK.
37 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_INSCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | loc.do-phu |  |  | 104 | 104 | 104 | 1.84 | 1 | Ready for review |  | 2020-03-11 | 2020-03-06 | 2020-03-10 | NG | 97 | 95 | 100 | Cant cover 100%. Owner said that's fine. | Fixed comment, function switch. Add test script 2. Re-run OK.
38 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBAirMonitoring.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | loc.do-phu |  |  | 154 | 154 | 154 | 2.73 | 2 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | NG | 98 | 96 | 100 | Cant cover 100%. Owner said that's fine. | Fixed comment, function switch.
39 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBBrakeFluidChange.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | loc.do-phu |  |  | 167 | 167 | 167 | 2.96 | 2 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 | Cant cover 100% when (RBFS_RBAPLEOLValvesToggling==RBFS_RBAPLEOLValvesToggling_OFF). Owner said that's fine. | Fixed comment, function switch.
40 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBComfortPulseCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | loc.do-phu |  |  | 147 | 147 | 147 | 2.61 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 | Cant cover 100% when (RBFS_RBAPLEOLComfortPulseCalib == RBFS_RBAPLEOLComfortPulseCalib_OFF). Owner said that's fine.
41 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBDynamicTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | loc.do-phu |  |  | 254 | 254 | 254 | 4.51 | 3 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 | Cant cover 100% when (RBFS_RBAPLEOLDynamicTest == RBFS_RBAPLEOLDynamicTest_OFF). Owner said that's fine.
42 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBEvacAndFill.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 193 | 193 |  | 3.43 | 2 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 100 | 100 | 91 | Bug, con not cover MCDC beacause this is true case for above condition
43 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBLeakageAndAirTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 204 | 204 |  | 3.62 | 3 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
44 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBRepairBleed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 194 | 194 |  | 3.44 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
45 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBRPSCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 141 | 141 |  | 2.5 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | NG | 98 | 95 | 100 | Bug (Condition is always TRUE)
46 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBTandemMasterCylinderTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 190 | 190 | 190 | 3.37 | 4 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 66 | 100 | 100 | OPL It does not impact to SW functionality.
47 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_SteeringAngleSensorCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 107 | 107 | 107 | 1.9 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 99 | 96 | 100 | OPL It does not impact to SW functionality.
48 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_WheelSpeedSensorTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 269 | 269 | 269 | 4.78 | 3 | Pending for OPL |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 99 | 97 | 100 | OPL It does not impact to SW functionality.
49 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_WDBI_IPBAssemblyMode.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 70 | 70 |  | 1.24 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
50 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_RBDI_NVMData_Common.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 204 | 204 | 204 | 3.62 | 3 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-06 | OK | 100 | 100 | 100
51 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_EcuReset.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 185 | 185 | 185 | 3.28 | 3 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-06 | OK | 100 | 100 | 100
52 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_GeneralFunctions.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | duong.nguyen |  |  | 68 | 68 | 68 | 1.2 | 1 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
53 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_NVMGeneric.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | duong.nguyen |  |  | 150 | 150 | 150 | 2.66 | 2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
54 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_RDBI_VehicleSpeed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 25 | 25 | 25 | 0.44 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
55 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_EOLDelayCtrlOrAPBMi.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 487 | 487 |  | 8.65 | 2.4 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
56 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RDBI_WheelSpeed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 110 | 110 | 110 | 1.95 | 2 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
57 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RoutineControl_EOLTable.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | chung.ly |  |  | 167 | 167 |  | 2.96 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
58 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RoutineControl_SpeedLimit.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 42 | 42 | 42 | 0.74 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
59 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RoutineControl_VRShutdown.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 40 | 40 | 40 | 0.71 | 0.3 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
60 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_WDBI_NVMData_ESP.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) | [5 empty] | 44 | 44 |  | 0.78 |  | N/A |  | 2020-03-11 | [6 empty] | dupplicate
61 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RBDI_NVMData_ESP.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 29 | 29 | 29 | 0.51 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
62 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_WheelSpeed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 110 | 110 | 110 | 1.95 | 1.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
63 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_SpeedLimit.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 42 | 42 | 42 | 0.74 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
64 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_WDBI_NVMData_ESP.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  |  | thanh.nguyen-kim |  |  | 44 | 44 | 44 | 0.78 | 0.7 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
65 | 20200305 | PSW | MC_227282_SGMW_E200_Plus_ESPCPiGen9.3_BSS04_SP02 | rb\as\core\app\asw\apbmi\host\PDM\APBPbcVariantItem_C\SRC\ | 1359400 | PbcVariantItem_PersistentData.c | Auto | - | SGMW_ESP93_Carbon_Int | - | XU Sherry (CC-AS/EVA-SW2-CN) |  |  | thanh.nguyen-kim |  |  | 117 | 117 | 117 | 2.08 | 3 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
66 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RbNetPrj\RBNet_Can\src\ | 1357606 | NET_CheckSumLib_CNMS.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS/EVA-SW32-CN) |  |  | thanh.nguyen-kim |  |  | 55 | 122 | 122 | 2.16 | 1.5 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 | Actually ELOC = 122
67 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1357606 | NET_SCL_Tx_SGMW_AyCompensationExport.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS/EVA-SW32-CN) |  |  | thanh.nguyen-kim |  |  | 60 | 60 | 60 | 1.06 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
68 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1357606 | NET_SCL_Tx_SGMW_TPMF.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS/EVA-SW32-CN) |  |  | thanh.nguyen-kim |  |  | 30 | 30 | 30 | 0.53 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
69 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1357606 | SGMW_RBA_NDS_Belt_Door_Callout.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS/EVA-SW32-CN) |  |  | thanh.nguyen-kim |  |  | 34 | 34 | 34 | 0.6 | 0.3 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
70 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1357606 | SGMW_RBA_NDS_HBCRequest_Callout.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS/EVA-SW32-CN) |  |  | chung.ly |  |  | 357 | 357 |  | 6.34 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
71 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1357606 | SGMW_RBA_NDS_SystemInfo_Callout.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS/EVA-SW32-CN) |  |  | chung.ly |  |  | 431 | 431 |  | 7.66 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
72 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\fawcore\app\tpms\MW\Common\src\ | 1357257 | TPMS_Handler_COMMON_CN.c | Manual | - | FAW_MainPath_V2.0_Int | - | JIN Li (CC-AS/EVA-SW33-CN) |  |  | chung.ly |  |  | 1993 | 1993 |  | 35.43 | 3 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | NG | 100 | 100 | 100 | Tool Issue
73 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\fawcore\app\tpms\MW\Common\src\ | 1357257 | TPMS_NvM_COMMON_CN.c | Manual | - | FAW_MainPath_V2.0_Int | - | JIN Li (CC-AS/EVA-SW33-CN) |  |  | chung.ly |  |  | 489 | 489 |  | 8.69 | 2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
74 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\fawcore\app\tpms\MW\Common\src\ | 1357257 | TPMS_PSW_Interface_COMMON_CN.c | Manual | - | FAW_MainPath_V2.0_Int | - | JIN Li (CC-AS/EVA-SW33-CN) |  |  | thanh.nguyen-kim |  |  | 593 | 587 | 587 | 10.43 | 5.8 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-12 | OK | 100 | 100 | 100
75 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\fawcore\app\dsm\RBWarningIndicator\src\ | 1357355 | Dem_PrjSpecificIndiHandling.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | duong.nguyen |  |  | 165 | 165 |  | 2.93 | 3 | N/A |  | 2020-03-12
76 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\asw\apbmi\host\PDM\APBHostData_Project_C\SRC\ | 1357355 | ApbHostData_Project.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | chung.ly |  |  | 8 | 8 | 8 | 0.14 | 0.2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
77 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | 1357355 | NET_AliveCounterLib_CNMS.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | chung.ly |  |  | 71 | 71 |  | 1.26 | 0.5 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
78 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | 1357355 | NET_CheckSumLib_CNMS.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | chung.ly |  |  | 55 |  |  | 0 | 0.5 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
79 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | 1357355 | NET_ChecksumLib_CNMS_Crc1850.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | chung.ly |  |  | 64 |  |  | 0 | 0.5 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
80 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | 1357355 | NET_MonitoringClasses_F30.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | chung.ly |  |  | 69 | 69 |  | 1.22 | 0.2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
81 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\obd\ObdCvnCalId\src\ | 1357355 | Obd_CalId.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | chung.ly |  |  | 5 |  |  | 0 | 0.1 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 |  | - | - | - | No code for test
82 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\dsmpr\src\Cubas\ESM\EcuM\src\ | 1357355 | EcuM_stub.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | chung.ly |  |  | 3 | 3 | 3 | 0.05 | 0.2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
83 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\dsmpr\src\ | 1357355 | RBPduHandler_Callouts.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | duong.nguyen |  |  | 220 | 220 | 220 | 3.91 | 3 | N/A |  | 2020-03-12
84 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\hswpr\tst\hswsim\src\ | 1357355 | TestEnvironment_Fee_EV711101.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | duong.nguyen |  |  | 4 | 4 | 4 | 0.07 | 0 | N/A |  | 2020-03-12 | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100
85 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\varcode | 1357355 | CNMS_Var_DcmRead.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | duong.nguyen |  |  | 12 | 12 | 12 | 0.21 | 0.1 | N/A |  | 2020-03-12 | 2020-03-12 | 2020-03-12 |  | - | - | - | No have function for test
86 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\varcode | 1357355 | CNMS_Var_Global.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS/EVA-SW1-CN) |  |  | duong.nguyen |  |  | 37 | 37 | 37 | 0.65 | 0.2 | N/A |  | 2020-03-12 | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100
87 | 20200309 | PSW | 221259_FAW_C105EV_L2_ESPhev_BL62 | rb\as\fawhevx\fawcore\app\net\RBScl\src\ | 1364387 | ComScl_Scl_Complex_proc.c | Auto | 99478 | FAW_Carbon_TypeF_Hevx_Int | - | HU Evan (CC-AS/EVA-SW33-CN) | [5 empty] | 67 |  |  | 0
88 | 20200309 | PSW | FAW_Carbon_TypeF_IBooster_Int | rb\as\faw\core\app\net\net_OBD_Off\RBScl\src\ | 1362438 | NET_Monitoring.c | Auto | BB97499 | FAW_Carbon_TypeF_IBooster_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | thanh.nguyen-kim |  |  | 130 | 288 |  | 5.12 | 4 |  |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100
89 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\core\app\dcom\rbapleol\src\ | 1362431 | RBAPLEOL_ValvesToggling.c | Auto | BB81433 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS/EVA-SW31-CN) |  |  | loc.do-phu |  |  | 1703 | 1703 | 1703 | 30.27 | 8 | Ready for review |  |  | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
90 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\core\app\dcom\RBAPLCust\src\ESP\ | 1362431 | RBAPLCUST_RDBI_IOCtrlState.c | Auto | BB81434 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS/EVA-SW31-CN) |  |  | thanh.nguyen-kim |  |  | 144 | 165 | 165 | 2.93 | 1 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100
91 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\core\app\dcom\RBAPLCust\src\common\ | 1362431 | RBAPLCUST_RDBI_SnapshotRead.c | Auto | BB81435 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS/EVA-SW31-CN) |  |  | loc.do-phu |  |  | 111 | 111 | 111 | 1.97 | 1 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100
92 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\CpiwAPB\app\asw\aswif\src\ | 1362431 | DNCIF_DTCOnCan.c | Auto | BB81436 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS/EVA-SW31-CN) |  |  | loc.do-phu |  |  | 12 | 12 |  | 0.21 | 0.1 | Ready for review |  |  | 2020-03-12 | 2020-03-12 |  | - | - | - | No function to test.
93 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\core\app\dcom\RBAPLCust\src\common\ | 1362431 | RBAPLCUST_DTCOnCan.c | Auto | BB81437 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS/EVA-SW31-CN) |  |  | thanh.nguyen-kim |  |  | 191 | 191 | 191 | 3.39 | 0.2 | Ready for review |  |  | 2020-03-12 | 2020-03-12 |  | - | - | - | No function to test.
94 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | \RBVAR\src\ | 1362409 | RBVAR_SystemStateManagement_COMMON.c | Auto | BB81033 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS/EVA-SW31-CN) |  |  | loc.do-phu |  |  | 21 | 131 |  | 2.32 | 6.9 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100
95 | 20200309 | PSW | MC_228919_SGMW_CN202C_ABS9.3CBi_Carbon_BSS02_SP02 | \RBScl\RBScl_BB80507\src\ | 1362280 | ComScl_Scl_ComplexProc_BB80507.c | Auto | 80507 | SGMW_ABS93_MS_Int | - | Pham Duc Trung (RBVH/EAS11) |  |  | thanh.nguyen-kim |  |  | 25 | 25 | 25 | 0.44 | 0.2 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100
96 | 20200309 | PSW | MC_228919_SGMW_CN202C_ABS9.3CBi_Carbon_BSS02_SP02 | \RBScl\RBScl_SGMW\src\src_xmt\ | 1362280 | NET_SCL_Tx_SystemInfo.c | Auto | 80507 | SGMW_ABS93_MS_Int | - | Pham Duc Trung (RBVH/EAS11) |  |  | thanh.nguyen-kim |  |  | 151 | 151 | 151 | 2.68 | 0.8 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100
97 | 20200309 | PSW | MC_228919_SGMW_CN202C_ABS9.3CBi_Carbon_BSS02_SP02 | \src\ | 1362280 | RBAPLCUST_ReadDTC.c | Auto | 80507 | SGMW_ABS93_MS_Int | - | Pham Duc Trung (RBVH/EAS11) |  |  | duong.nguyen |  |  | 178 | 178 | 178 | 3.16 | 3 | Ready for review
98 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\CpiwAPB\app\dsm\RBHMI\src\ | 1362197 | RBHMI_ConfigOutputDriver_PRJ.c | Auto | 81033 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | LI Xiaoyu (CC-AS/EVA-SW2-CN) |  |  | thanh.nguyen-kim |  |  | 280 | 277 | 277 | 4.92 | 2 | Ready for review |  |  | 2020-03-13 | 2020-03-13 | OK | 100 | 100 | 100
99 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\core\app\dcom\RBAPLCust\src\common\ | 1362163 | RBAPLCUST_DiagnosticSessionControl.c | Auto | 81033 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | LESLIE PUTHOOR Milda (CC-AS/EVA-SW31-CN) |  |  | duong.nguyen |  |  | 259 | 259 | 259 | 4.6 | 3
100 | 20200309 | PSW | MC_227282_SGMW_E200_Plus_ESPCPiGen9.3_BSS04 | rb\as\sgmw\CN210S\app\dsm\RBVAR\src\ | 1360524 | RBVAR_SystemStateManagement_PROJECT.c | Auto | none | SGMW_ESP93_Carbon_Int | - | DIAO Aimei (CC-AS/EVA-SW32-CN) | [5 empty] | 35 |  |  | 0
101 | 20200312 | PSW | 221259_FAW_C105EV_L2_ESPhev_BL62 | rb\as\cnms_core\app\net\scl_callout\src\ | 1368920 | RBA_NDS_ESP_2_Callout.c | Auto | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | duong.nguyen |  |  | 191 |  |  | 0
102 | 20200312 | PSW | 221259_FAW_C105EV_L2_ESPhev_BL62 | rb\as\fawhevx\fawcore\app\net\RBScl\src\ | 1368920 | ComScl_Scl_Complex_proc.c | Auto | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) | [5 empty] | 67 |  |  | 0
103 | 20200312 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1368889 | SGMW_RBA_NDS_SystemInfo_Callout.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS/EVA-SW32-CN) |  |  | duong.nguyen |  |  | 431 |  |  | 0
104 | 20200312 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1368889 | NET_SCL_Rx_SGMW_RemoteControl.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS/EVA-SW32-CN) |  |  | chung.ly |  |  | 184 |  |  | 0
105 | 20200312 | PSW | BYD_IPB_SW_Mainstream_BL05_SP09 |  | 1359407 | NET_SCL_Rx_SystemInfo.c | Auto |  | BYD_IPB_BL05_Int | - | GUO Sasa (CC-AS/EVA-SW3-CN) |  |  | thanh.nguyen-kim |  |  | 1023 |  |  | 0
106 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | ComScl_RxPdu_WorkingMode_Monitor.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS/EVA-SW31-CN) | [5 empty] | 43 |  |  | 0
107 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | NET_SCL_Rx_EngineSpeed.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS/EVA-SW31-CN) |  |  | thanh.nguyen-kim |  |  | 231 |  |  | 0
108 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | NET_SCL_Rx_GearBox.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS/EVA-SW31-CN) |  |  | chung.ly |  |  | 360 |  |  | 0
109 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | NET_SCL_Rx_SystemInfo.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS/EVA-SW31-CN) |  |  | loc.do-phu |  |  | 1023 | 1023 | 1000 | 18.18 | 8
110 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | NET_SCL_Rx_TCU.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS/EVA-SW31-CN) |  |  | loc.do-phu |  |  | 303 |  |  | 0
111 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | NET_SCL_Rx_VAF_Complex.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS/EVA-SW31-CN) | [5 empty] | 87 |  |  | 0
112 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | RBA_NDS_Complex_Callout.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS/EVA-SW31-CN) |  |  | duong.nguyen |  |  | 828 |  |  | 0
113 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | RBA_NDS_WheelOdoEdges_Callout.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS/EVA-SW31-CN) | [5 empty] | 107 |  |  | 0
114 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl\ | 1264979 | rba_SCL_Settings.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS/EVA-SW31-CN) |  |  | chung.ly |  |  | 1193 |  |  | 0 |  |  |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100
115 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl\ | 1264979 | RBNET_Scl_Complexsignals.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS/EVA-SW31-CN) | [5 empty] | 23 |  |  | 0
116 | 20200312 | ASW | HHT_VX1_ESPHevX_BL2_Sprint3 | - | 1367009 | CM_IVC_RWS_Status |  |  | 1371465_1367009.zip | 1.2 | ZHANG Ruipeng (BEG/ESW-CN) |  |  | duong.nguyen |  |  | 18 lines |  |  | 3 |  |  |  | 20200320
117 | 20200312 | ASW | HHT_VX1_ESPHevX_BL2_Sprint3 | - | 1367009 | CM_IVC_ModeHandling |  |  | 1371465_1367009.zip | 2.1.805.3 | ZHANG Ruipeng (BEG/ESW-CN) | [5 empty] | 15 lines, 2 array |  |  | 5 |  |  |  | 20200320
118 | 20200312 | ASW | HHT_VX1_ESPHevX_BL2_Sprint3 | - | 1366969 | VDCVAFS_PreindicatorArbitrator |  |  | 1366969.zip | 1.1 | ZHANG Ruipeng (BEG/ESW-CN) |  |  | loc.do-phu |  |  | 8 lines |  |  | 3 |  |  |  | 20200320
119 | 20200312 | ASW | HHT_VX1_ESPHevX_BL2_Sprint3 | - | 1366969 | VDCVAFS_VDCActiveArbitrator |  |  | 1366969.zip | 1 | ZHANG Ruipeng (BEG/ESW-CN) |  |  | thanh.nguyen-kim |  |  | 8 lines |  |  | 3 |  |  |  | 20200320
120 | 20200312 | ASW | HHT_VX1_ESPHevX_BL2_Sprint3 | - | 1371465 | CM_IVC_HHT_HADPADActivation |  |  | 1371465_1367009.zip | 1.1 | ZHANG Ruipeng (BEG/ESW-CN) | [5 empty] | 62 lines |  |  | 7 |  |  |  | 20200320
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
Table KPI ASW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | duong.nguyen | 50 | 50 | 0.375 | 133.3333 | 100%
2 | loc.do-phu | 0 | 0 | 0 | N/A | N/A
3 | thanh.nguyen-kim | 19 | 19 | 0.5 | 38 | 100%
4 | chung.ly | 0 | 0 | 0 | N/A | N/A
Table KPI PSW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | duong.nguyen | 2636 | 1939 | 4.8125 | 402.9091 | 73.56%
2 | loc.do-phu | 6074 | 5051 | 8.25 | 612.2424 | 83.16%
3 | thanh.nguyen-kim | 4959 | 4671 | 7.675 | 608.5993 | 94.19%
4 | chung.ly | 6502 | 6502 | 6.8438 | 950.0639 | 100%
Note on A27: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Purple must be complete before 11-03
Note on I27: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be run Tool Auto Comment to generate header and add cmt in section "Test Goal"
Note on K69: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): \\hc-ut40745c\Ban_Vien_external\DB\05-march
Note on A74: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Yellow must be complete before 12-03 EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45):
Note on K74: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): \\hc-ut40745c\Ban_Vien_external\DB\04-march
Note on I76: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be use "Auto Comment"
Note on A89: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Orange must be complete before 13_Mar
Note on B103: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be complete before 17_Mar

## Sheet1
ComponentName | ItemName
rb\as\gaig\prj\dsmpr\src\RBVoltageHandler\src | RBVoltageHandler_Suppression.c
rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src | SGMW_RBA_NDS_HBCRequest_Callout.c
rb\as\gaig\A10\dsmpr\src\RBHMI\src | RBHMI_LDMLamp_CNMS.c
rb\as\cnms_core\app\obd\ObdCyclesHandler\src | ObdCyclesHandler.c
- | PAP_Odometry
rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | RBAPLCUST_EOLDelayCtrlOrAPBMi.c
rb\as\sgmw\core\app\dcom\RBAPLCust\src\ESP | RBAPLCUST_RDBI_TPMS.c
rb\as\sgmw\core\app\dcom\RBAPLCust\src\ESP | RBAPLCUST_RoutineControl_TPMSReset.c
rb\as\gaig\A10\app\net\RBScl\RBSclGAC\src | RB_SCL_GAC_RX.c
rb\as\gaig\A10\app\net\RBScl\RBSclGAC\src | RB_SCL_GAC_TX.c
rb\as\cnms_core\app\net\scl\LDMFunctions\ACC\src | NET_SCL_Tx_AEB.c
rb\as\cnms_core\app\net\scl\LDMFunctions\APA\src | NET_SCL_Tx_APAInformSts.c
rb\as\BYD\ipb\app\net\RBScl\Scl_Callout\src | RBA_NDS_Complex_Callout.c
rb\as\gwm\core\app\dcom\RBAPLCust\src | RBAPLCUST_RBDI_NVMData.c
rb\as\gwm\core\app\dcom\RBAPLCust\src | RBAPLCUST_RDBI_PBCData.c
rb\as\gwm\core\app\net\scl\Callout\src\ATMwithoutSportPlus | NET_ATM_Callout_GWM.c
rb\as\gwm\core\app\net\scl\Callout\src\ATMwithSportPlus | NET_ATM_Callout_GWM.c
rb\as\cnms_core\app\net\scl_callout\ | RBA_NDS_ABS_3_Callout.c
rb\as\cnms_core\app\net\scl_callout\ | RBA_NDS_APC_1_Callout.c
rb\as\cnms_core\app\net\scl_callout\ | RBA_NDS_ESP_3_Callout.c
rb\as\cnms_core\app\net\scl_callout\ | RBA_NDS_HCU_PT_10_Callout.c
rb\as\cnms_core\app\net\scl_callout\ | RBA_NDS_HCU_PT_2_Callout.c
rb\as\cnms_core\app\net\scl_callout\ | RBA_NDS_SystemInfo.c
- | HDC_InvalidThrPos
rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | RBAPLCUST_RDBI_AnalogData.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | RBAPLCUST_RDBI_StatusInformation.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | RBAPLCUST_RoutineControl_iBoosterActuatorTest.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_InputOutputControl.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_InputOutputControl_GeneralFunctions.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RDBI_ActuationState.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RDBI_CBDS.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RDBI_IOCtrlState.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RDBI_IPBAssemblyMode.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RDBI_PBC.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RDBI_SystemData.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RDBI_SystemSensor.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_INSCalibration.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_IPBAirMonitoring.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_IPBBrakeFluidChange.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_IPBComfortPulseCalibration.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_IPBDynamicTest.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_IPBEvacAndFill.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_IPBLeakageAndAirTest.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_IPBRepairBleed.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_IPBRPSCalibration.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_IPBTandemMasterCylinderTest.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_SteeringAngleSensorCalibration.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_WheelSpeedSensorTest.c
rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_WDBI_IPBAssemblyMode.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\common | RBAPLCUST_RBDI_NVMData_Common.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\common | RBAPLCUST_EcuReset.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\common | RBAPLCUST_GeneralFunctions.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\common | RBAPLCUST_NVMGeneric.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\common | RBAPLCUST_RDBI_VehicleSpeed.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | RBAPLCUST_EOLDelayCtrlOrAPBMi.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | RBAPLCUST_RDBI_WheelSpeed.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | RBAPLCUST_RoutineControl_EOLTable.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | RBAPLCUST_RoutineControl_SpeedLimit.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | RBAPLCUST_RoutineControl_VRShutdown.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_WDBI_NVMData_ESP.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RBDI_NVMData_ESP.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RDBI_WheelSpeed.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_RoutineControl_SpeedLimit.c
rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | RBAPLCUST_WDBI_NVMData_ESP.c
rb\as\core\app\asw\apbmi\host\PDM\APBPbcVariantItem_C\SRC\ | PbcVariantItem_PersistentData.c
\rb\as\sgmw\CN210S\app\net\RbNetPrj\RBNet_Can\src\ | NET_CheckSumLib_CNMS.c
\rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | NET_SCL_Tx_SGMW_AyCompensationExport.c
\rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | NET_SCL_Tx_SGMW_TPMF.c
\rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | SGMW_RBA_NDS_Belt_Door_Callout.c
\rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | SGMW_RBA_NDS_HBCRequest_Callout.c
\rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | SGMW_RBA_NDS_SystemInfo_Callout.c
rb\as\fawMP\fawcore\app\tpms\MW\Common\src\ | TPMS_Handler_COMMON_CN.c
rb\as\fawMP\fawcore\app\tpms\MW\Common\src\ | TPMS_NvM_COMMON_CN.c
rb\as\fawMP\fawcore\app\tpms\MW\Common\src\ | TPMS_PSW_Interface_COMMON_CN.c
rb\as\fawMP\fawcore\app\dsm\RBWarningIndicator\src\ | Dem_PrjSpecificIndiHandling.c
rb\as\fawMP\prjConf\app\asw\apbmi\host\PDM\APBHostData_Project_C\SRC\ | ApbHostData_Project.c
rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | NET_AliveCounterLib_CNMS.c
rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | NET_CheckSumLib_CNMS.c
rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | NET_ChecksumLib_CNMS_Crc1850.c
rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | NET_MonitoringClasses_F30.c
rb\as\fawMP\prjConf\app\obd\ObdCvnCalId\src\ | Obd_CalId.c
rb\as\fawMP\prjConf\dsmpr\src\Cubas\ESM\EcuM\src\ | EcuM_stub.c
rb\as\fawMP\prjConf\dsmpr\src\ | RBPduHandler_Callouts.c
rb\as\fawMP\prjConf\hswpr\tst\hswsim\src\ | TestEnvironment_Fee_EV711101.c
rb\as\fawMP\prjConf\varcode | CNMS_Var_DcmRead.c
rb\as\fawMP\prjConf\varcode | CNMS_Var_Global.c
rb\as\fawhevx\fawcore\app\net\RBScl\src\ | ComScl_Scl_Complex_proc.c
rb\as\faw\core\app\net\net_OBD_Off\RBScl\src\ | NET_Monitoring.c
rb\as\core\app\dcom\rbapleol\src\ | RBAPLEOL_ValvesToggling.c
rb\as\saic\core\app\dcom\RBAPLCust\src\ESP\ | RBAPLCUST_RDBI_IOCtrlState.c
rb\as\saic\core\app\dcom\RBAPLCust\src\common\ | RBAPLCUST_RDBI_SnapshotRead.c
rb\as\saic\CpiwAPB\app\asw\aswif\src\ | DNCIF_DTCOnCan.c
rb\as\saic\core\app\dcom\RBAPLCust\src\common\ | RBAPLCUST_DTCOnCan.c
\RBVAR\src\ | RBVAR_SystemStateManagement_COMMON.c
\RBScl\RBScl_BB80507\src\ | ComScl_Scl_ComplexProc_BB80507.c
\RBScl\RBScl_SGMW\src\src_xmt\ | NET_SCL_Tx_SystemInfo.c
\src\ | RBAPLCUST_ReadDTC.c
rb\as\saic\CpiwAPB\app\dsm\RBHMI\src\ | RBHMI_ConfigOutputDriver_PRJ.c
rb\as\saic\core\app\dcom\RBAPLCust\src\common\ | RBAPLCUST_DiagnosticSessionControl.c
rb\as\sgmw\CN210S\app\dsm\RBVAR\src\ | RBVAR_SystemStateManagement_PROJECT.c
Total Day | Status (%)
0 | N/A
0 | N/A
0 | N/A
0 | N/A
0 | N/A
0 | N/A
0 | N/A
0 | N/A
Total Day | Status (%)
0 | N/A
0 | N/A
0 | N/A
0 | N/A
0 | N/A
0 | N/A
0 | N/A
0 | N/A

## Template
No | Package | Type | Project | ComponentName | TaskID | ItemName | ItemRevision | Task Jira | TaskGroup | Tester | LOC | LOC Complete | Estimation hour | Actual hour | Status | Planned Start | Planned End | Start | End | C0 | C1 | MCDC | Reason
1 | 1 | PSW | GAC_220680_Carbon_A18_ESPHevx_FPA/RPA_BL03 | rb\as\gaig\prj\dsmpr\src\RBVoltageHandler\src\ | 1348323 | RBVoltageHandler_Suppression.c | - | N/A |  |  | 113 |  | 2 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
2 | 1 | PSW | MC_227282_SGMW_E200_Plus_ESPCPiGen9.3_BSS04_SP02 | rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1345876 | SGMW_RBA_NDS_HBCRequest_Callout.c | - | N/A |  |  | 148 |  | 2.63 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
3 | 1 | PSW | 241595_GAC_A27_ESP9.3CP_BL04 | rb\as\gaig\A10\dsmpr\src\RBHMI\src\ | 1350941 | RBHMI_LDMLamp_CNMS.c | - | N/A |  |  | 291 |  | 5.17 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
4 | 1 | PSW | 223331_GAC_A39_Carbon_ESP9.3HD_OBD_BL07 | rb\as\cnms_core\app\obd\ObdCyclesHandler\src\ | 1351929 | ObdCyclesHandler.c | - | N/A |  |  | 254 |  | 4.51 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
5 | 1 | ASW | DFN_ESP_Gen9.3_532EC_244112_BSS01 | - | 1351929 | PAP_Odometry | 4.2.104.1 | N/A |  |  | 19 |  | 1.16 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
6 | 2 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | RBAPLCust\src\ESP\ | 1351848 | RBAPLCUST_EOLDelayCtrlOrAPBMi.c | - | N/A |  |  | 478 |  | 8.49 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
7 | 2 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | RBAPLCust\src\ESP\ | 1351848 | RBAPLCUST_RDBI_TPMS.c | - | N/A |  |  | 286 |  | 5.08 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
8 | 2 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | RBAPLCust\src\ESP\ | 1351848 | RBAPLCUST_RoutineControl_TPMSReset.c | - | N/A |  |  | 110 |  | 1.95 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
Table KPI ASW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
3 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
5 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
6 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
7 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
9 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
10 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
3
Table KPI PSW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
3

## Table
KPI Table
No\Type | ASW | PSW
1 | 130 | 450
Table Type of Testing
No | Type | Tool | Detail Output
1 | ASW | ATT | 1. Test Design (.xls) 2. Plot File (.plt) 3. ATT project 4. Coverage Log
2 | PSW | Cantata | 1. TPA file (.tpa) 2. test report (.html) 3. test report (.xml) 4. test summary (.html) 5. File Coverage Fail Reason (.xls)
Table Tester
No | Member
1 | hieu.nguyen-trung
2 | hau.nguyen-tai
3 | bang.nguyen-duy
4 | dac.luu-cong
5 | duong.nguyen
6 | loc.do-phu
7 | thanh.nguyen-kim
8 | chung.ly
Status Table
No | Status
1 | N/A |  | COEM process: test-->review test----(feedback no finding)-->generate WT----(review WT no finding)---> done task Tức là bên anh gửi UT output cho internal => Có OPL có bug => Internal review OK => Làm walkthrough => Sau đó internal review Walkthrough => Send email cho External confirm OK => Mark Done
2 | Ongoing
3 | Ready for review
4 | Ready for delivery
5 | Ready for PLC
6 | Pending for OPL
7 | Complete & Closed

## Template_Weekly_Report
Date | 2020-02-03
Total Days | 20
1. Completed ELOCs of the team from the beginning of Month (Mar) till Now:
|  | # | Types | Assigned ELOCs | Completed ELOCs | Status (%) (Completed/Assigned)
|  | 1 | PSW | ??? | ??? | ???
|  | 2 | ASW | ??? | ??? | ???
2. Completed ELOCs of each member from the beginning of Month (Mar) till Now:
|  | # | External Name | PSW ELOCs | ASW ELOCs
|  | 1 | hieu.nguyen-trung | ??? | ???
|  | 2 | duong.nguyen-tuan | ??? | ???
3. Risks/ Pending Issues:
|  | # | Risks/ Issues
1
2
4. Found Defects/ OPLs in Month (Mar):
|  | # | Defects / OPLs
1
2
5. Leave Plan (Mar):
|  | # | External Name | Num of Day | Detail
|  | 1 | hieu.nguyen-trung | ??? | ???
|  | 2 | duong.nguyen-tuan | ??? | ???
Note:
Productivity of each Member per Day
PSW: 450 ELOCs
ASW: 150 ELOCs
Total Productivity per Month
PSW: 450x4x20 = 36,000 ELOCs
ASW: 130x4x20 = 10,400 ELOCs

## Check_List
Location
| + Location Internal Project: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project
| + Location Internal Your Output: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project\001_Prj\01_COEM\01_Output_Package
Please ensure your push correct the Package name with the TaskGroup
| + Location Internal Your Release Output: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project\001_Prj\01_COEM\02_Release_Package
| + Location for delivery to internal team: | \\hc-ut40745c\Ban_Vien_external\Release\Gen_9.3