## COEM_Package_20200302
No | Package | Type | Project | ComponentName | TaskID | ItemName | Type of Comment | BB | Database | ItemRevision | Owner Contact | Task Jira | Tester | PeerReviewer | Status Review | ELOC Assigned | ELOC Recheck With Tool | LOC Complete | Estimation base TOOL | Actual hour | Status | Planned Start | Planned End | Start | End | Status Result | C0 | C1 | MCDC | Reason | Remark
1 | 20200302 | PSW | GAC_220680_Carbon_A18_ESPHevx_FPA\RPA_BL03 | rb\as\gaig\prj\dsmpr\src\RBVoltageHandler\src | 1348323 | RBVoltageHandler_Suppression.c | Auto | - | GAC_ESPHevX_HADHAP_Int | - | CHEN Xiaomin (CC-AS\EVA-SW31-CN) |  | duong.nguyen | hieu.nguyen-trung | Yes | 113 | 113 | 113 | 3 | 3 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-03 | OK | 100 | 100 | 100
2 | 20200302 | PSW | MC_227282_SGMW_E200_Plus_ESPCPiGen9.3_BSS04_SP02 | rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src | 1345876 | SGMW_RBA_NDS_HBCRequest_Callout.c | Auto | bb99885 | SGMW_ESP93_Carbon_Int | - | WANG Yang (CC-AS\EVA-SW32-CN) |  | loc.do-phu | hieu.nguyen-trung | Yes | 148 | 357 | 357 | 10 | 6 | Ready for review | 2020-03-03 | 2020-03-04 | 2020-03-02 | 2020-03-02 | OK | 100 | 100 | 100 | Tool collect 148 ELOC, but the real is 357
3 | 20200302 | PSW | 241595_GAC_A27_ESP9.3CP_BL04 | rb\as\gaig\A10\dsmpr\src\RBHMI\src | 1350941 | RBHMI_LDMLamp_CNMS.c | Auto | BB81650 & BB81651 | Gac_ESP93CP_A26HD_Int | - | MIAO Huafeng (CC-AS\EVA-SW32-CN) |  | duong.nguyen | hieu.nguyen-trung | Yes | 291 | 291 | 291 | 8 | 10 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-03 | OK | 100 | 100 | 100 | Wrong extension C "RBHMI_LDMLamp_CNMS.C" | Got 1 findings
4 | 20200302 | PSW | 223331_GAC_A39_Carbon_ESP9.3HD_OBD_BL07 | rb\as\cnms_core\app\obd\ObdCyclesHandler\src | 1351929 | ObdCyclesHandler.c | Auto | bb99735 | GAC_ESP93CP_Carbon_Int | - | CHEN Xiaomin (CC-AS\EVA-SW31-CN) |  | chung.ly | hieu.nguyen-trung | Yes | 254 | 254 | 254 | 4.51 | 10 | Pending for OPL | 2020-03-02 | 2020-03-03 | 2020-03-02 | 2020-03-03 | NG | 100 | 100 | 95 | Bug (Condition is always TRUE) so can not cover MCDC. | Got 1 defect Reason: not send to internal team
5 | 20200302 | ASW | DFN_ESP_Gen9.3_532EC_244112_BSS01 | - | 1352219 | PAP_Odometry | Auto | - | 1352219 | V4.2.104.1 | QIAN Li (CC-AS\EVA-SW2-CN) |  | thanh.nguyen-kim | hieu.nguyen-trung | Yes | 19 | 19 | 19 | 1.16 | 4 | Pending for OPL | 2020-03-02 | 2020-03-03 | 2020-03-03 | 2020-03-03 | NG | 95.6 | 96 | - | Bug (Condition is always TRUE) | Got 1 findings
6 | 20200302 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1351848 | RBAPLCUST_EOLDelayCtrlOrAPBMi.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | SUN Yun (CC-AS\EVA-SW31-CN) |  | thanh.nguyen-kim | hieu.nguyen-trung | Yes | 478 | 478 | 478 | 8.49 | 14 | Ready for PLC | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-04 | NG | 99 | 99 | 100 | Bug (Condition not occur) | Got 1 findings
7 | 20200302 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | rb\as\sgmw\core\app\dcom\RBAPLCust\src\ESP | 1351848 | RBAPLCUST_RDBI_TPMS.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | SUN Yun (CC-AS\EVA-SW31-CN) |  | loc.do-phu | hieu.nguyen-trung | Yes | 286 | 286 | 286 | 5.08 | 1 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-03 | 2020-03-02 | OK | 100 | 100 | 100 |  | -
8 | 20200302 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | 299 | 1351848 | RBAPLCUST_RoutineControl_TPMSReset.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | SUN Yun (CC-AS\EVA-SW31-CN) |  | chung.ly | hieu.nguyen-trung | Yes | 110 | 110 | 110 | 1.95 | 4 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100 |  | -
9 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\gaig\A10\app\net\RBScl\RBSclGAC\src | 1278532 | RB_SCL_GAC_RX.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS\EVA-SW31-CN) |  | loc.do-phu | hieu.nguyen-trung | Yes | 251 | 294 | 294 | 5.22 | 6.5 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-03 | 2020-03-03 | OK | 100 | 100 | 100 | Actually ELOC = 294 | -
10 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\gaig\A10\app\net\RBScl\RBSclGAC\src | 1278532 | RB_SCL_GAC_TX.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS\EVA-SW31-CN) |  | loc.do-phu | hieu.nguyen-trung | Yes | 101 | 101 | 101 | 1.79 | 1.5 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100 |  | -
11 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\cnms_core\app\net\scl\LDMFunctions\ACC\src | 1278532 | NET_SCL_Tx_AEB.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS\EVA-SW31-CN) |  | duong.nguyen |  |  | 90 | 90 | 90 | 1.6 | 3 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | NG | 86 | 83 | 100 |  | -
12 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\cnms_core\app\net\scl\LDMFunctions\APA\src | 1278532 | NET_SCL_Tx_APAInformSts.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS\EVA-SW31-CN) |  | loc.do-phu | hieu.nguyen-trung | Yes | 101 | 183 | 183 | 3.25 | 3 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100 | Actually ELOC = 183 | -
13 | 20200303 | PSW | BYD_IPB_SW_Mainstream_BL05 | rb\as\BYD\ipb\app\net\RBScl\Scl_Callout\src | 1352115 | RBA_NDS_Complex_Callout.c | Auto | none | BYD_IPB_BL05_Int | - | GUO Sasa (CC-AS\EVA-SW3-CN) |  | chung.ly |  |  | 828 | 828 | 828 | 14.72 | 16 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-04 | 2020-03-06 | NG | 100 | 100 | 98 | Bug (Condition is always TRUE) | -
14 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\dcom\RBAPLCust\src | 1353313 | RBAPLCUST_RBDI_NVMData.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH\EAS12) |  | loc.do-phu |  |  | 371 | 371 | 371 | 6.59 | 3 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100 | OPL It does not impact to SW functionality. | -
15 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\dcom\RBAPLCust\src | 1353313 | RBAPLCUST_RDBI_PBCData.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH\EAS12) |  | loc.do-phu |  |  | 254 | 254 | 254 | 4.51 | 2 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100 |  | -
16 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\net\scl\Callout\src\ATMwithoutSportPlus | 1353313 | NET_ATM_Callout_GWM.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH\EAS12) |  | thanh.nguyen-kim |  |  | 395 | 395 | 395 | 7.02 | 5 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100 |  | -
17 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\net\scl\Callout\src\ATMwithSportPlus | 1353313 | NET_ATM_Callout_GWM.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH\EAS12) |  | thanh.nguyen-kim |  |  | 395 | 395 | 395 | 7.02 | 5 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100 |  | -
18 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_ABS_3_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS\EVA-SW33-CN) |  | duong.nguyen | duong.nguyen | Yes | 96 | 96 | 96 | 1.7 | 3 | Ready for delivery |  | 2020-03-09 | 2020-03-06 | 2020-03-06 | NG | 97 | 95 | 92 | OPL is already feedback, confirm it can be ignore | -
19 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_APC_1_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS\EVA-SW33-CN) |  | loc.do-phu | duong.nguyen | Yes | 28 | 28 | 28 | 0.49 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100 |  | -
20 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_ESP_3_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS\EVA-SW33-CN) |  | loc.do-phu | duong.nguyen | Yes | 36 | 36 | 36 | 0.64 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100 |  | -
21 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_HCU_PT_10_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS\EVA-SW33-CN) |  | chung.ly | duong.nguyen | Yes | 80 | 80 | 80 | 1.42 | 2 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | NG | 100 | 100 | 75 | Bug, con not cover MCDC beacause this is true case for above condition | -
22 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_HCU_PT_2_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS\EVA-SW33-CN) |  | loc.do-phu | duong.nguyen | Yes | 33 | 33 | 33 | 0.58 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100 |  | -
23 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_SystemInfo.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS\EVA-SW33-CN) |  | thanh.nguyen-kim | duong.nguyen | Yes | 212 | 212 | 212 | 3.76 | 2 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100 |  | -
24 | 20200303 | ASW | - | - | 1353762 | HDC_InvalidThrPos | Auto | - | 1353762 | V3.3.147305.2 | Nguyen Quang Vinh (RBVH\EAS15) |  | duong.nguyen |  |  | 50 | 50 | 50 | 3.07 | 6 | Ready for review | 2020-03-02 | 2020-03-06 | 2020-03-05 | 2020-03-06 |  |  |  |  | Have issues with database, complexity of code | -
25 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | 1341660 | RBAPLCUST_RDBI_AnalogData.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | duong.nguyen |  |  | 77 | 77 | 77 | 1.36 | 2.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
26 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | 1341660 | RBAPLCUST_RDBI_StatusInformation.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | duong.nguyen |  |  | 44 | 44 | 44 | 0.78 | 1 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
27 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | 1341660 | RBAPLCUST_RoutineControl_iBoosterActuatorTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | duong.nguyen |  |  | 210 | 210 | 210 | 3.73 | 5 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100 | No code | -
28 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_InputOutputControl.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | duong.nguyen |  |  | 622 | 622 | 622 | 11.05 | 11 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100 | - | -
29 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_InputOutputControl_GeneralFunctions.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 97 | 97 | 97 | 1.72 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100 |  | -
30 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_ActuationState.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 100 | 100 | 100 | 1.77 | 0.75 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100 |  | -
31 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_CBDS.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 8 | 8 | 8 | 0.14 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 |  | - | - | - | No code, already confirmed with Mr.Hai | -
32 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_IOCtrlState.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 148 | 148 | 148 | 2.63 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100 |  | -
33 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_IPBAssemblyMode.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 17 | 17 | 17 | 0.3 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
34 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_PBC.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 18 | 18 | 18 | 0.32 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
35 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_SystemData.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | loc.do-phu |  |  | 129 | 129 | 129 | 2.29 | 3 | Ready for delivery |  | 2020-03-11 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100 |  | Fixed comment
36 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_SystemSensor.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | loc.do-phu |  |  | 164 | 196 | 196 | 3.48 | 4 | Ready for review |  | 2020-03-11 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100 |  | Fixed comment, function switch. Re-run OK.
37 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_INSCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | loc.do-phu |  |  | 104 | 104 | 104 | 1.84 | 1 | Ready for review |  | 2020-03-11 | 2020-03-06 | 2020-03-10 | NG | 97 | 95 | 100 | Cant cover 100%. Owner said that's fine. | Fixed comment, function switch. Add test script 2. Re-run OK.
38 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBAirMonitoring.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | loc.do-phu |  |  | 154 | 154 | 154 | 2.73 | 2 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | NG | 98 | 96 | 100 | Cant cover 100%. Owner said that's fine. | Fixed comment, function switch.
39 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBBrakeFluidChange.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | loc.do-phu |  |  | 167 | 167 | 167 | 2.96 | 2 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 | Cant cover 100% when (RBFS_RBAPLEOLValvesToggling==RBFS_RBAPLEOLValvesToggling_OFF). Owner said that's fine. | Fixed comment, function switch.
40 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBComfortPulseCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | loc.do-phu |  |  | 147 | 147 | 147 | 2.61 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 | Cant cover 100% when (RBFS_RBAPLEOLComfortPulseCalib == RBFS_RBAPLEOLComfortPulseCalib_OFF). Owner said that's fine. | -
41 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBDynamicTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | loc.do-phu |  |  | 254 | 254 | 254 | 4.51 | 3 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 | Cant cover 100% when (RBFS_RBAPLEOLDynamicTest == RBFS_RBAPLEOLDynamicTest_OFF). Owner said that's fine. | -
42 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBEvacAndFill.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 193 | 193 | 193 | 3.43 | 3 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 100 | 100 | 91 | Bug, con not cover MCDC beacause this is true case for above condition | -
43 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBLeakageAndAirTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 204 | 204 | 204 | 3.62 | 3.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
44 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBRepairBleed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 194 | 194 | 194 | 3.44 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
45 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBRPSCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 141 | 141 | 141 | 2.5 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | NG | 98 | 95 | 100 | Bug (Condition is always TRUE) | -
46 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBTandemMasterCylinderTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 190 | 190 | 190 | 3.37 | 4 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 66 | 100 | 100 | OPL It does not impact to SW functionality. | -
47 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_SteeringAngleSensorCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 107 | 107 | 107 | 1.9 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 99 | 96 | 100 | OPL It does not impact to SW functionality. | -
48 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_WheelSpeedSensorTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 269 | 269 | 269 | 4.78 | 3 | Pending for OPL |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 99 | 97 | 100 | OPL It does not impact to SW functionality. | -
49 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_WDBI_IPBAssemblyMode.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 70 | 70 | 70 | 1.24 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
50 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_RBDI_NVMData_Common.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 204 | 204 | 204 | 3.62 | 3 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-06 | OK | 100 | 100 | 100 |  | -
51 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_EcuReset.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 185 | 185 | 185 | 3.28 | 3 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-06 | OK | 100 | 100 | 100 |  | -
52 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_GeneralFunctions.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | duong.nguyen |  |  | 68 | 68 | 68 | 1.2 | 2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
53 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_NVMGeneric.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | duong.nguyen |  |  | 150 | 150 | 150 | 2.66 | 4 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
54 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_RDBI_VehicleSpeed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 25 | 25 | 25 | 0.44 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
55 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_EOLDelayCtrlOrAPBMi.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 487 | 487 | 487 | 8.65 | 2.4 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100 |  | -
56 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RDBI_WheelSpeed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 110 | 110 | 110 | 1.95 | 2 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100 |  | -
57 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RoutineControl_EOLTable.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | chung.ly |  |  | 167 | 167 | 167 | 2.96 | 2 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100 |  | -
58 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RoutineControl_SpeedLimit.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 42 | 42 | 42 | 0.74 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
59 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RoutineControl_VRShutdown.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 40 | 40 | 40 | 0.71 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
60 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_WDBI_NVMData_ESP.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  |  |  |  | 44 | 44 | 44 | 0.78 |  | N/A |  | 2020-03-11 | [6 empty] | dupplicate
61 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RBDI_NVMData_ESP.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 29 | 29 | 29 | 0.51 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
62 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_WheelSpeed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 110 | 110 | 110 | 1.95 | 1.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
63 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_SpeedLimit.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 42 | 42 | 42 | 0.74 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
64 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_WDBI_NVMData_ESP.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS\ESW2-CN) |  | thanh.nguyen-kim |  |  | 44 | 44 | 44 | 0.78 | 0.7 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
65 | 20200305 | PSW | MC_227282_SGMW_E200_Plus_ESPCPiGen9.3_BSS04_SP02 | rb\as\core\app\asw\apbmi\host\PDM\APBPbcVariantItem_C\SRC\ | 1359400 | PbcVariantItem_PersistentData.c | Auto | - | SGMW_ESP93_Carbon_Int | - | XU Sherry (CC-AS\EVA-SW2-CN) |  | thanh.nguyen-kim |  |  | 117 | 117 | 117 | 2.08 | 3 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
66 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RbNetPrj\RBNet_Can\src\ | 1357606 | NET_CheckSumLib_CNMS.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS\EVA-SW32-CN) |  | thanh.nguyen-kim |  |  | 55 | 122 | 122 | 2.16 | 2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 | Actually ELOC = 122 | -
67 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1357606 | NET_SCL_Tx_SGMW_AyCompensationExport.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS\EVA-SW32-CN) |  | thanh.nguyen-kim |  |  | 60 | 60 | 60 | 1.06 | 1 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
68 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1357606 | NET_SCL_Tx_SGMW_TPMF.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS\EVA-SW32-CN) |  | thanh.nguyen-kim |  |  | 30 | 30 | 30 | 0.53 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
69 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1357606 | SGMW_RBA_NDS_Belt_Door_Callout.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS\EVA-SW32-CN) |  | thanh.nguyen-kim |  |  | 34 | 34 | 34 | 0.6 | 0.3 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
70 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1357606 | SGMW_RBA_NDS_HBCRequest_Callout.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS\EVA-SW32-CN) |  | chung.ly |  |  | 357 | 357 | 357 | 6.34 | 6 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
71 | 20200305 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1357606 | SGMW_RBA_NDS_SystemInfo_Callout.c | Auto | - | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS\EVA-SW32-CN) |  | chung.ly |  |  | 431 | 431 | 431 | 7.66 | 7 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100 |  | -
72 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\fawcore\app\tpms\MW\Common\src\ | 1357257 | TPMS_Handler_COMMON_CN.c | Manual | - | FAW_MainPath_V2.0_Int | - | JIN Li (CC-AS\EVA-SW33-CN) |  | chung.ly |  |  | 1993 | 1993 | 1993 | 35.43 | 3 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | NG | 100 | 100 | 100 | Tool Issue | -
73 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\fawcore\app\tpms\MW\Common\src\ | 1357257 | TPMS_NvM_COMMON_CN.c | Manual | - | FAW_MainPath_V2.0_Int | - | JIN Li (CC-AS\EVA-SW33-CN) |  | chung.ly |  |  | 489 | 489 | 489 | 8.69 | 8 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
74 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\fawcore\app\tpms\MW\Common\src\ | 1357257 | TPMS_PSW_Interface_COMMON_CN.c | Manual | - | FAW_MainPath_V2.0_Int | - | JIN Li (CC-AS\EVA-SW33-CN) |  | thanh.nguyen-kim |  |  | 593 | 587 | 587 | 10.43 | 10 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
75 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\fawcore\app\dsm\RBWarningIndicator\src\ | 1357355 | Dem_PrjSpecificIndiHandling.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | duong.nguyen |  |  | 165 | 165 | 165 | 2.93 | 3 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
76 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\asw\apbmi\host\PDM\APBHostData_Project_C\SRC\ | 1357355 | ApbHostData_Project.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | chung.ly |  |  | 8 | 8 | 8 | 0.14 | 0.2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
77 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | 1357355 | NET_AliveCounterLib_CNMS.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | chung.ly |  |  | 71 | 71 | 71 | 1.26 | 1 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
78 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | 1357355 | NET_CheckSumLib_CNMS.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | chung.ly |  |  | 55 | 55 | 55 | 0.97 | 0.5 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
79 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | 1357355 | NET_ChecksumLib_CNMS_Crc1850.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | chung.ly |  |  | 64 | 64 | 64 | 1.13 | 0.5 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
80 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\net\RbNetPrj\RBNet_Can\src\ | 1357355 | NET_MonitoringClasses_F30.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | chung.ly |  |  | 69 | 69 | 69 | 1.22 | 1.2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
81 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\app\obd\ObdCvnCalId\src\ | 1357355 | Obd_CalId.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | chung.ly |  |  | 5 | 5 | 5 | 0.08 | 0.1 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 |  | - | - | - | No code for test | -
82 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\dsmpr\src\Cubas\ESM\EcuM\src\ | 1357355 | EcuM_stub.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | chung.ly |  |  | 3 | 3 | 3 | 0.05 | 0.2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
83 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\dsmpr\src\ | 1357355 | RBPduHandler_Callouts.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | duong.nguyen |  |  | 220 | 220 | 220 | 3.91 | 4 | Ready for review |  | 2020-03-12 | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
84 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\hswpr\tst\hswsim\src\ | 1357355 | TestEnvironment_Fee_EV711101.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | duong.nguyen |  |  | 4 | 4 | 4 | 0.07 | 0.5 | Ready for review |  | 2020-03-12 | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
85 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\varcode | 1357355 | CNMS_Var_DcmRead.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | duong.nguyen |  |  | 12 | 12 | 12 | 0.21 | 0 | N/A |  | 2020-03-12 | 2020-03-12 | 2020-03-12 |  | - | - | - | No have function for test | -
86 | 20200304 | PSW | 225378_FAW_D357_High_BL31 | rb\as\fawMP\prjConf\varcode | 1357355 | CNMS_Var_Global.c | Manual | - | FAW_MainPath_V2.0_Int | - | SUN Nan (CC-AS\EVA-SW1-CN) |  | duong.nguyen |  |  | 37 | 37 | 37 | 0.65 | 1 | Ready for review |  | 2020-03-12 | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
87 | 20200309 | PSW | 221259_FAW_C105EV_L2_ESPhev_BL62 | rb\as\fawhevx\fawcore\app\net\RBScl\src\ | 1364387 | ComScl_Scl_Complex_proc.c | Auto | 99478 | FAW_Carbon_TypeF_Hevx_Int | - | HU Evan (CC-AS\EVA-SW33-CN) |  | chung.ly |  |  | 67 | 67 | 67 | 1.19 | 1.15 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
88 | 20200309 | PSW | FAW_Carbon_TypeF_IBooster_Int | rb\as\faw\core\app\net\net_OBD_Off\RBScl\src\ | 1362438 | NET_Monitoring.c | Auto | BB97499 | FAW_Carbon_TypeF_IBooster_Int | - | HU Evan (CC-AS\EVA-SW33-CN) |  | thanh.nguyen-kim |  |  | 130 | 288 | 288 | 5.12 | 9 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
89 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\core\app\dcom\rbapleol\src\ | 1362431 | RBAPLEOL_ValvesToggling.c | Auto | BB81433 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS\EVA-SW31-CN) |  | loc.do-phu |  |  | 1703 | 1703 | 1703 | 30.27 | 8 | Ready for review |  |  | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100 |  | -
90 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\core\app\dcom\RBAPLCust\src\ESP\ | 1362431 | RBAPLCUST_RDBI_IOCtrlState.c | Auto | BB81434 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS\EVA-SW31-CN) |  | thanh.nguyen-kim |  |  | 144 | 165 | 165 | 2.93 | 2.5 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
91 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\core\app\dcom\RBAPLCust\src\common\ | 1362431 | RBAPLCUST_RDBI_SnapshotRead.c | Auto | BB81435 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS\EVA-SW31-CN) |  | loc.do-phu |  |  | 111 | 111 | 111 | 1.97 | 1 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
92 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\CpiwAPB\app\asw\aswif\src\ | 1362431 | DNCIF_DTCOnCan.c | Auto | BB81436 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS\EVA-SW31-CN) |  | loc.do-phu |  |  | 12 | 12 | 12 | 0.21 | 0.1 | Ready for review |  |  | 2020-03-12 | 2020-03-12 |  | - | - | - | No function to test. | -
93 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\core\app\dcom\RBAPLCust\src\common\ | 1362431 | RBAPLCUST_DTCOnCan.c | Auto | BB81437 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS\EVA-SW31-CN) |  | thanh.nguyen-kim |  |  | 191 | 191 | 191 | 3.39 | 3 | Ready for review |  |  | 2020-03-12 | 2020-03-12 |  | - | - | - | No function to test. | -
94 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | \RBVAR\src\ | 1362409 | RBVAR_SystemStateManagement_COMMON.c | Auto | BB81033 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | FANG Amanda (CC-AS\EVA-SW31-CN) |  | loc.do-phu |  |  | 21 | 131 | 131 | 2.32 | 6.9 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
95 | 20200309 | PSW | MC_228919_SGMW_CN202C_ABS9.3CBi_Carbon_BSS02_SP02 | \RBScl\RBScl_BB80507\src\ | 1362280 | ComScl_Scl_ComplexProc_BB80507.c | Auto | 80507 | SGMW_ABS93_MS_Int | - | Pham Duc Trung (RBVH\EAS11) |  | thanh.nguyen-kim |  |  | 25 | 25 | 25 | 0.44 | 0.2 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
96 | 20200309 | PSW | MC_228919_SGMW_CN202C_ABS9.3CBi_Carbon_BSS02_SP02 | \RBScl\RBScl_SGMW\src\src_xmt\ | 1362280 | NET_SCL_Tx_SystemInfo.c | Auto | 80507 | SGMW_ABS93_MS_Int | - | Pham Duc Trung (RBVH\EAS11) |  | thanh.nguyen-kim |  |  | 151 | 151 | 151 | 2.68 | 2.5 | Ready for review |  |  | 2020-03-12 | 2020-03-12 | OK | 100 | 100 | 100 |  | -
97 | 20200309 | PSW | MC_228919_SGMW_CN202C_ABS9.3CBi_Carbon_BSS02_SP02 | rb\as\sgmw\core\app\dcom\RBAPLCust\src | 1362280 | RBAPLCUST_ReadDTC.c | Auto | 80507 | SGMW_ABS93_MS_Int | - | Pham Duc Trung (RBVH\EAS11) |  | duong.nguyen |  |  | 178 | 178 | 178 | 3.16 | 4 | Ready for review | [9 empty] | -
98 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\CpiwAPB\app\dsm\RBHMI\src\ | 1362197 | RBHMI_ConfigOutputDriver_PRJ.c | Auto | 81033 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | LI Xiaoyu (CC-AS\EVA-SW2-CN) |  | thanh.nguyen-kim |  |  | 280 | 277 | 277 | 4.92 | 2 | Ready for review |  |  | 2020-03-13 | 2020-03-13 | OK | 100 | 100 | 100 |  | -
99 | 20200309 | PSW | SAIC EP22 M2 withDA ESP9.3 BSS02 | rb\as\saic\core\app\dcom\RBAPLCust\src\common\ | 1362163 | RBAPLCUST_DiagnosticSessionControl.c | Auto | 81033 | SAIC_A_ARCH_CMP_ESP93_Carbon_Int | - | LESLIE PUTHOOR Milda (CC-AS\EVA-SW31-CN) |  | duong.nguyen |  |  | 259 | 259 | 259 | 4.6 | 6 | Ready for review |  |  | 2020-03-13 | 2020-03-13 | NG | 100 | 100 | 94 | Owner confirm could be ignore | -
100 | 20200309 | PSW | MC_227282_SGMW_E200_Plus_ESPCPiGen9.3_BSS04 | rb\as\sgmw\CN210S\app\dsm\RBVAR\src\ | 1360524 | RBVAR_SystemStateManagement_PROJECT.c | Auto | none | SGMW_ESP93_Carbon_Int | - | DIAO Aimei (CC-AS\EVA-SW32-CN) |  | thanh.nguyen-kim |  |  | 35 | 35 | 35 | 0.62 | 0.5 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
101 | 20200312 | PSW | 221259_FAW_C105EV_L2_ESPhev_BL62 | rb\as\cnms_core\app\net\scl_callout\src\ | 1368920 | RBA_NDS_ESP_2_Callout.c | Auto | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS\EVA-SW33-CN) |  | duong.nguyen |  |  | 191 | 191 | 191 | 3.39 | 5 | Ready for review |  | 2020-03-14 |  |  | OK | 100 | 100 | 100 |  | -
102 | 20200312 | PSW | 221259_FAW_C105EV_L2_ESPhev_BL62 | rb\as\fawhevx\fawcore\app\net\RBScl\src\ | 1368920 | ComScl_Scl_Complex_proc.c | Auto | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS\EVA-SW33-CN) |  | chung.ly |  |  | 67 | 67 | 67 | 1.19 | 0.5 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 | Please check with task ID: 1364387 | -
103 | 20200312 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1368889 | SGMW_RBA_NDS_SystemInfo_Callout.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS\EVA-SW32-CN) |  | duong.nguyen |  |  | 431 | 431 | 431 | 7.66 | 8 | Ready for review |  |  | 2020-03-17 | 2020-03-17 | OK | 100 | 100 | 100 |  | -
104 | 20200312 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | \rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1368889 | NET_SCL_Rx_SGMW_RemoteControl.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | BAO Eric (CC-AS\EVA-SW32-CN) |  | chung.ly |  |  | 184 | 184 | 184 | 3.27 | 2 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
105 | 20200312 | PSW | BYD_IPB_SW_Mainstream_BL05_SP09 |  | 1359407 | NET_SCL_Rx_SystemInfo.c | Auto |  | BYD_IPB_BL05_Int | - | GUO Sasa (CC-AS\EVA-SW3-CN) |  | thanh.nguyen-kim |  |  | 1023 | 1023 | 1023 | 18.18 | 12 | Ready for review |  |  |  |  | OK | 100 | 100 | 100 |  | -
106 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | ComScl_RxPdu_WorkingMode_Monitor.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS\EVA-SW31-CN) |  | loc.do-phu |  |  | 43 | 43 | 43 | 0.76 | 1 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
107 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | NET_SCL_Rx_EngineSpeed.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS\EVA-SW31-CN) |  | thanh.nguyen-kim |  |  | 231 | 231 | 231 | 4.1 | 3 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
108 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | NET_SCL_Rx_GearBox.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS\EVA-SW31-CN) |  | chung.ly |  |  | 360 | 360 | 360 | 6.4 | 3 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
109 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | NET_SCL_Rx_SystemInfo.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS\EVA-SW31-CN) |  | loc.do-phu |  |  | 1023 | 1023 | 1023 | 18.18 | 8 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
110 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | NET_SCL_Rx_TCU.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS\EVA-SW31-CN) |  | loc.do-phu |  |  | 303 | 303 | 303 | 5.38 | 2 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
111 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | NET_SCL_Rx_VAF_Complex.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS\EVA-SW31-CN) |  | loc.do-phu |  |  | 87 | 87 | 87 | 1.54 | 2 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
112 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | RBA_NDS_Complex_Callout.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS\EVA-SW31-CN) |  | duong.nguyen |  |  | 828 | 828 | 828 | 14.72 | 8 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | NG | 100 | 100 | 95 | Owner confirm could be ignore | -
113 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl_Callout\ | 1264979 | RBA_NDS_WheelOdoEdges_Callout.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS\EVA-SW31-CN) |  | loc.do-phu |  |  | 107 | 107 | 107 | 1.9 | 2 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
114 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl\ | 1264979 | rba_SCL_Settings.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS\EVA-SW31-CN) |  | chung.ly |  |  | 1193 | 1193 | 1193 | 21.2 | 1 | Ready for review |  |  | 2020-03-12 | 2020-03-16 | OK | 100 | 100 | 100 |  | -
115 | 20200312 | PSW | BYD_Carbon_Mainstream_BL01 | \MainstreamF30\rb\as\byd\Bydcarbon\app\net\RBScl\ | 1264979 | RBNET_Scl_Complexsignals.c | Auto | 81728 | BYD_Carbon_ESP93_Int | - | LI Zhiyuan (CC-AS\EVA-SW31-CN) |  | loc.do-phu |  |  | 23 | 23 | 23 | 0.4 | 1 | Ready for review |  |  | 2020-03-16 | 2020-03-16 | NG | 87 | 50 | 0 | Owner said it doesn’t affect the project | -
116 | 20200313 | PSW | GWM_ESP9.3_CHB071_HP_RC2 | rb\as\core\hwp\cubas\Diagnosis | 1371489 | DemCSMosar_EventLogger.c | Auto | 81923 | GWM_CHB071HevX_Carbon_Int | - | Nguyen Duc Huong Quynh (RBVH\EAS12) |  | duong.nguyen |  |  | 194 | 194 | 194 | 3.44 | 3 | Ready for review |  | 2020-03-18 |  | 2020-03-18 | OK | 100 | 100 | 100 |  | -
117 | 20200313 | PSW | GWM_ESP9.3_CHB071_HP_RC2 | rb\as\core\hwp\cubas\Diagnosis | 1371489 | RBDsm_Measurement.c | Auto | 81923 | GWM_CHB071HevX_Carbon_Int | - | Nguyen Duc Huong Quynh (RBVH\EAS12) |  | duong.nguyen |  |  | 2 | 2 | 2 | 0.03 | 0.03 | Ready for review |  | 2020-03-18 |  | 2020-03-18 | OK | 100 | 100 | 100 |  | -
118 | 20200313 | PSW | FAW_HQEV_2WD_MC | rb\as\core\app\net | 1355916 | RBCAN_CanSMBusOffRecovery.c | Manual | - | FAW_MainPathHEV_Int | - | JIN Li (CC-AS\EVA-SW33-CN) |  | chung.ly |  |  | 28 | 28 | 28 | 0.49 | 1 | Complete & Closed |  | 2020-03-18 | 2020-03-19 | 2020-03-19 | OK | 100 | 100 | 100 | Raised OPL : Improvement code swap two api | -
119 | 20200313 | PSW | FAW_HQEV_2WD_MC | rb\as\fawMPHev\prjConf\app\net | 1355916 | NET_SCL_Tx_APBMi.c | Manual | - | FAW_MainPathHEV_Int | - | JIN Li (CC-AS\EVA-SW33-CN) |  | chung.ly |  |  | 226 | 226 | 226 | 4.01 | 1 | Complete & Closed |  | 2020-03-18 | 2020-03-18 | 2020-03-18 | NG | 100 | 100 | 97 | Raised OPL | -
120 | 20200313 | PSW | FAW_HQEV_2WD_MC | rb\as\fawMPHev\prjConf\app\net | 1355916 | NET_SCL_Rx_HHC.c | Manual | - | FAW_MainPathHEV_Int | - | JIN Li (CC-AS\EVA-SW33-CN) |  | loc.do-phu |  |  | 77 | 77 | 77 | 1.36 | 2 | Complete & Closed |  | 2020-03-18 | 2020-03-18 | 2020-03-18 | OK | 100 | 100 | 100 |  | -
121 | 20200312 | ASW | HHT_VX1_ESPHevX_BL2_Sprint3 | - | 1367009 | CM_IVC_RWS_Status | - | - | 1371465_1367009.zip | 1.2 | ZHANG Ruipeng (BEG\ESW-CN) |  | duong.nguyen |  |  | 18 | 18 | 18 | 3 | 2 | Ready for delivery |  | 2020-03-19 | 2020-03-19 | 2020-03-20 | OK | 100 | 100 | 100 |  | -
122 | 20200312 | ASW | HHT_VX1_ESPHevX_BL2_Sprint3 | - | 1367009 | CM_IVC_ModeHandling | - | - | 1371465_1367009.zip | 2.1.805.3 | ZHANG Ruipeng (BEG\ESW-CN) |  | loc.do-phu |  |  | 15 | 15 | 15 | 5 | 8 | Ready for delivery |  | 2020-03-17 |  | 2020-03-20 | OK | 100 | 100 | 100 |  | -
123 | 20200312 | ASW | HHT_VX1_ESPHevX_BL2_Sprint3 | - | 1366969 | VDCVAFS_PreindicatorArbitrator | - | - | 1366969.zip | 1.1 | ZHANG Ruipeng (BEG\ESW-CN) |  | loc.do-phu |  |  | 8 | 8 | 8 | 3 | 1 | Ready for delivery |  | 2020-03-17 | 2020-03-23 | 2020-03-23 | OK | 100 | 100 | 100 |  | -
124 | 20200312 | ASW | HHT_VX1_ESPHevX_BL2_Sprint3 | - | 1366969 | VDCVAFS_VDCActiveArbitrator | - | - | 1366969.zip | 1 | ZHANG Ruipeng (BEG\ESW-CN) |  | thanh.nguyen-kim |  |  | 8 | 8 | 8 | 3 | 2.3 | Ready for review |  | 2020-03-17 | 2020-03-23 | 2020-03-23 | OK | 100 | 100 | 100 |  | -
125 | 20200312 | ASW | HHT_VX1_ESPHevX_BL2_Sprint3 | - | 1371465 | CM_IVC_HHT_HADPADActivation | - | - | 1371465_1367009.zip | 1.1 | ZHANG Ruipeng (BEG\ESW-CN) |  | duong.nguyen |  |  | 62 | 62 | 62 | 7 | 5 | Ready for delivery |  | 2020-03-17 | 2020-03-23 | 2020-03-20 | OK | 100 | 100 | 100 |  | -
125 | 20200317 | ASW | 239689_NIO_G1.3&G1.F_ESPHevX_BSS03_SP01 | - | 1345833 | CDD_SsmSelContr | - | - | 1345833.zip | 4.0.146322.0 | WANG Zhenyu (CC-AS\EVA-SW2-CN) |  | duong.nguyen |  |  | 15 | 15 | 15 | 0.92 | 2 | Ready for delivery |  | 2020-03-17 | 2020-03-23 | 2020-03-20 | OK | 100 | 100 | 100 |  | -
126 | 20200317 | PSW | E111_ESPHevx_BSL30 | rba\Bldr_FAW | 1376431 | rba_BldrCmp_Cfg_Functions.c | Manual | 80773 | FAW_E111_ESPHevX_Int | - | Chitra Chandrasekaran (RBEI\EBB7) |  | loc.do-phu |  |  | 154 | 154 | 154 |  | 1 | Ready for delivery |  | 2020-03-17 |  | 2020-03-20 | NG | 95 | 85 | 100 | - Cant cover true case if (*length_pu16 > maxLength_u16) at line 95 - Cant cover false case if (retValue == E_OK) at line 276 Owner said it doesn’t affect the project | -
127 | 20200317 | PSW | E111_ESPHevx_BSL30 | rba\Bldr_FAW | 1376431 | rba_BldrCmp_Cfg_NvmIf.c | Manual | 80773 | FAW_E111_ESPHevX_Int | - | Chitra Chandrasekaran (RBEI\EBB7) |  | loc.do-phu |  |  | 120 | 120 | 120 |  | 2 | Ready for delivery |  | 2020-03-17 |  | 2020-03-20 | OK | 100 | 100 | 100 |  | -
128 | 20200317 | PSW | E111_ESPHevx_BSL30 | rba\Bldr_FAW | 1376431 | rba_BldrCmp_Cfg_CheckMem.c | Manual | 80773 | FAW_E111_ESPHevX_Int | - | Chitra Chandrasekaran (RBEI\EBB7) |  | thanh.nguyen-kim |  |  | 145 | 145 | 145 |  | 3 | Ready for delivery |  | 2020-03-17 | 2020-03-23 | 2020-03-23 | OK | 100 | 100 | 100 |  | -
129 | 20200317 | PSW | Geely_KC2A_ESP9.3_HB_225750_BB8033_BL04_SP01 | rb\as\geely\core\app\dcom\RBAPLCust\src\ | 1375562 | RBAPLCUST_RBDI_NVMData.c | Auto | - | Geely_Beryllium2_OBD_China6_Int | - | KASIVASAKAM Murugananth (CC-AS\EVA-SW32-CN) |  | loc.do-phu |  |  | 371 | 371 | 371 |  | 2 | Ready for delivery | 2020-03-17 | 2020-03-17 |  | 2020-03-20 | OK | 100 | 100 | 100 |  | -
130 | 20200317 | PSW | GAC_Carbon_Stream_ESPCP_BL04 | rb\as\gaig\core\app\dcom\RBAPLCust\src\common\ | 1324814 | RBAPLCUST_RBDI_VariandCode.c | Auto | 81262, 81708 | GAC_ESP93CP_Carbon_Int | - | PAN Qi (CC-AS/EVA-SW31-CN) |  | loc.do-phu |  |  | 32 | 209 | 209 |  | 2 | Ready for review |  | 2020-03-25 | 2020-03-19 | 2020-03-19 | OK | 100 | 100 | 100 |  | -
131 | 20200317 | PSW | GAC_Carbon_Stream_ESPCP_BL04 | rb\as\gaig\core\app\dcom\RBAPLCust\src\ESP\ | 1324814 | RBAPLCUST_RDBI_TPMS_GAC.c | Auto | 81262, 81709 | GAC_ESP93CP_Carbon_Int | - | PAN Qi (CC-AS/EVA-SW31-CN) |  | loc.do-phu |  |  | 80 | 80 | 80 |  | 2 | Ready for review |  | 2020-03-25 | 2020-03-19 | 2020-03-19 | OK | 100 | 100 | 100 |  | -
132 | 20200317 | PSW | GAC_Carbon_Stream_ESPCP_BL04 | rb\as\gaig\core\app\dcom\RBAPLCust\src\ESP\ | 1324814 | RBAPLCUST_WDBI_TPMS_GAC.c | Auto | 81262, 81710 | GAC_ESP93CP_Carbon_Int | - | PAN Qi (CC-AS/EVA-SW31-CN) |  | loc.do-phu |  |  | 38 | 38 | 38 |  | 2 | Ready for review |  | 2020-03-25 | 2020-03-19 | 2020-03-19 | OK | 100 | 100 | 100 |  | -
133 | 20200317 | PSW | GAC_Carbon_Stream_ESPCP_BL04 | rb\as\gaig\core\app\dcom\RBAPLCust\src\ESP\ | 1324814 | RBAPLCUST_RoutineControl_TPMSReset.c | Auto | 81262, 81711 | GAC_ESP93CP_Carbon_Int | - | PAN Qi (CC-AS/EVA-SW31-CN) |  | loc.do-phu |  |  | 110 | 110 | 110 |  | 1 | Ready for review |  | 2020-03-25 | 2020-03-19 | 2020-03-19 | OK | 100 | 100 | 100 |  | -
134 | 20200317 | PSW | GAC_Carbon_Stream_ESPCP_BL04 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP\ | 1324814 | RBAPLCUST_EOLDelayCtrlOrAPBMi.c | Auto | 81262, 81712 | GAC_ESP93CP_Carbon_Int | - | PAN Qi (CC-AS/EVA-SW31-CN) |  | duong.nguyen |  |  | 478 |  | 0 |  |  |  |  | 2020-03-25 | [7 empty] | -
135 | 20200317 | PSW | GAC_Carbon_Stream_ESPCP_BL04 | rb\as\gaig\core\app\dcom\Cubas\src\Dcm_CNMS\ | 1324814 | DcmAppl_DcmSwitchCommunicationControl.c | Auto | 81262, 81713 | GAC_ESP93CP_Carbon_Int | - | PAN Qi (CC-AS/EVA-SW31-CN) |  | loc.do-phu |  |  | 84 | 84 | 84 |  | 1 | Ready for review |  | 2020-03-25 | 2020-03-19 | 2020-03-19 | OK | 100 | 100 | 100 |  | -
136 | 20200317 | PSW | GAC_Carbon_Stream_ESPCP_BL04 | rb\as\gaig\core\app\dcom\RBAPLCust\src\common\ | 1324814 | RBAPLCUST_DiagnosticSessionControl.c | Auto | 81262, 81714 | GAC_ESP93CP_Carbon_Int | - | PAN Qi (CC-AS/EVA-SW31-CN) |  | duong.nguyen |  |  | 259 |  | 0 | [6 empty] | 2020-03-25 | [5 empty] | -
137 | 20200317 | PSW | 240688_DFSK_F517\527\537_EVR_Carbon_ESP9.3 | rb\as\dfsk\CpiwAPB\app\dsm\RBVAR\src\ | 1297584 | RBVAR_VarCode_PROJECT.c | Auto | - | DFSK_ESP_Carbon_Int | - | Nguyen Hiep Thanh (RBVH/EAS11) |  | thanh.nguyen-kim |  |  | 34 | 439 | 439 | 7 | 6 | Ready for review |  |  | 2020-03-19 | 2020-03-19 | NG | 100 | 100 | 36 | - Can't cover MCDC,C0,C1 for case have for loop because of not generating coverage. | -
138 | 20200317 | PSW | 240688_DFSK_F517\527\537_EVR_Carbon_ESP9.3 | rb\as\dfsk\CpiwAPB\app\net\RBScl\RBScl_DFSK\src\ | 1297584 | NET_Monitoring.c | Auto | - | DFSK_ESP_Carbon_Int | - | Nguyen Hiep Thanh (RBVH/EAS11) |  | thanh.nguyen-kim |  |  | 130 | 288 | 288 | 5.12 | 2 | Ready for review |  |  | 2020-03-19 | 2020-03-19 | OK | 100 | 100 | 100 |  | -
139 | 20200317 | PSW | 240688_DFSK_F517\527\537_EVR_Carbon_ESP9.3 | rb\as\dfsk\CpiwAPB\app\net\RBScl\RBScl_DFSK\src\ | 1297584 | NET_VAR_IsVcActive.c | Auto | - | DFSK_ESP_Carbon_Int | - | Nguyen Hiep Thanh (RBVH/EAS11) |  | thanh.nguyen-kim |  |  | 29 | 29 | 29 |  | 0.5 | Ready for review |  |  | 2020-03-23 | 2020-03-23 | OK | 100 | 100 | 100
140 | 20200317 | PSW | 240688_DFSK_F517\527\537_EVR_Carbon_ESP9.3 | rb\as\dfsk\CpiwAPB\app\net\RBScl\RBScl_DFSK\src\ | 1297584 | RBA_NDS_Rx_ASW_Callout.c | Auto | - | DFSK_ESP_Carbon_Int | - | Nguyen Hiep Thanh (RBVH/EAS11) |  | duong.nguyen |  |  | 162 |  | 0 | [6 empty] | 2020-03-25
141 | 20200317 | PSW | 240688_DFSK_F517\527\537_EVR_Carbon_ESP9.3 | rb\as\dfsk\CpiwAPB\app\net\RBScl\RBScl_DFSK\src\ | 1297584 | RBA_NDS_Rx_VAF_Callout.c | Auto | - | DFSK_ESP_Carbon_Int | - | Nguyen Hiep Thanh (RBVH/EAS11) |  | thanh.nguyen-kim |  |  | 95 | 95 | 95 |  | 1 | Ready for review |  |  | 2020-03-23 | 2020-03-23 | OK | 100 | 100 | 100
142 | 20200317 | PSW | 240688_DFSK_F517\527\537_EVR_Carbon_ESP9.3 | rb\as\dfsk\CpiwAPB\app\net\RBScl\RBScl_DFSK\src\ | 1297584 | RBA_NDS_Tx_ASW_Callout.c | Auto | - | DFSK_ESP_Carbon_Int | - | Nguyen Hiep Thanh (RBVH/EAS11) |  | duong.nguyen |  |  | 170 |  | 0 | [6 empty] | 2020-03-25
143 | 20200317 | PSW | 240688_DFSK_F517\527\537_EVR_Carbon_ESP9.3 | rb\as\dfsk\CpiwAPB\hswpr\tst\hswsim\src\ | 1297584 | TestEnvironment_Fee_EV702148.c | Auto | - | DFSK_ESP_Carbon_Int | - | Nguyen Hiep Thanh (RBVH/EAS11) |  | thanh.nguyen-kim |  |  | 10 | 10 | 10 |  | 0.5 | Ready for review |  |  | 2020-03-23 | 2020-03-23 | OK | 100 | 100 | 100
144 | 20200318 | PSW | Adapt_236234_SMART_VDDM_ESPHevX_BSS02_E2_SP2 | GEEA2.0\rb\as\cevt\Geely\app\dsm\RBVAR\src\ | 1375788 | VAR09_OutputDriver_CEVT.c | Auto | - | CEVT_GEEA_SMART_Deuterium_Int | - | ZHANG Guorong (CC-AS/EVA-SW32-CN) |  | thanh.nguyen-kim |  |  | 125 | 125 | 125 |  | 2 | Ready for review |  |  | 2020-03-23 | 2020-03-23 | OK | 100 | 100 | 100
145 | 20200318 | PSW | Adapt_236234_SMART_VDDM_ESPHevX_BSS02_E2_SP2 | GEEA2.0\rb\as\cevt\Geely\app\dsm\RBVAR\src\ | 1375788 | VAR09_IDDefinitionTable_CEVT.c | Auto | - | CEVT_GEEA_SMART_Deuterium_Int | - | ZHANG Guorong (CC-AS/EVA-SW32-CN) |  | thanh.nguyen-kim |  |  | 33 | 33 | 33 |  | 0.5 | Ready for review |  |  | 2020-03-23 | 2020-03-23 |  | - | - | - | No have function for test
146 | 20200318 | PSW | 235199_SAIC_EP21_MCE_ESP9.3HevX_BSS03_SP02 | ESPhevXSAICEP\rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src | 1373324 | rba_BldrCmp_Cfg_PrjFunctions.c | Auto | - | SAIC_EP_CMP_ESPHevX_Int | - | Moogambika Ratha Krishnan (RBEI/EBB7) |  | thanh.nguyen-kim |  |  | 178 |  | 0 | [6 empty] | 2020-03-26
147 | 20200318 | PSW | 235199_SAIC_EP21_MCE_ESP9.3HevX_BSS03_SP02 | ESPhevXSAICEP\rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src | 1373324 | rba_BldrCMP_Cfg_CRC.c | Auto | - | SAIC_EP_CMP_ESPHevX_Int | - | Moogambika Ratha Krishnan (RBEI/EBB7) |  | duong.nguyen |  |  | 196 |  | 0 | [6 empty] | 2020-03-26
148 | 20200319 | PSW | 235199_SAIC_EP21_MCE_ESP9.3HevX_BSS03_SP03 | rb\as\saicep\esphevx\app\net\RBScl\src\ | 1380105 | ComScl_Scl_Complex.c | Auto | - | SAIC_EP_CMP_ESPHevX_Int | - | TANG Yanqi (CC-AS/EVA-SW31-CN) |  | duong.nguyen |  |  | 417 |  | 0 | [6 empty] | 2020-03-26
149 | 20200313 | ASW | GAC_Carbon_RPA_iBooster_Mainpath_BL04 | - | 1366593 | PFA_ISC_SituationSupport | - | - | 1366593.zip | 1.0.147.2.1.3.147315.1 | CUI Jin (CC-AS/EVA-SW1-CN) |  | duong.nguyen |  |  | 104 | 104 | 104 | 6.4 | 6 | Ready for delivery |  | 2020-03-19 | 2020-03-20 | 2020-03-19 | OK | 100 | 100 | 100
150 | 20200319 | ASW | 233878_GAC_A20_CarbonESP9.3CP_BL04 | - | 1380028 | AvhSendSoftSwctrlst | - | - | 1380028.zip | v 1.1 | LIU Qiang (CC-AS/EVA-SW2-CN) |  |  |  |  | 14 |  | 0 | [6 empty] | 2020-03-27
151 | 20200319 | ASW | GAC_Carbon_Stream_ESPCP_BL04 | - | 1379963 | ApbDynConfig | - | - | 1379963.zip | (1.1.315.1) | QIU Liqi (CC-AS/EVA-SW2-CN) |  | loc.do-phu |  |  | 62 | 80 | 80 | [6 empty] | 2020-03-27
152 | 20200319 | ASW | GAC_Carbon_Stream_ESPCP_BL04 | - | 1379963 | EPBVirtualButtonSignalProcess | - | - | 1379963.zip | (1.0.315.0) | QIU Liqi (CC-AS/EVA-SW2-CN) |  |  |  |  | 32 |  | 0 | [6 empty] | 2020-03-27
153 | 20200319 | ASW | GAC_Carbon_Stream_ESPCP_BL04 | - | 1379963 | EPBButton_StpOnBrkProcess | - | - | 1379963.zip | v 1.0 | QIU Liqi (CC-AS/EVA-SW2-CN) |  |  |  |  | 11 |  | 0 | [6 empty] | 2020-03-27
154 | 20200319 | ASW | GAC_Carbon_Stream_ESPCP_BL04 | - | 1379963 | EPBButtonArbitration | - | - | 1379963.zip | v 1.0 | QIU Liqi (CC-AS/EVA-SW2-CN) |  |  |  |  | 19 |  | 0 | [6 empty] | 2020-03-27
155 | 20200319 | ASW | GAC_Carbon_Stream_ESPCP_BL04 | - | 1379963 | EPBVirtualButton_DragMode | - | - | 1379963.zip | (1.0.315.1) | QIU Liqi (CC-AS/EVA-SW2-CN) |  | duong.nguyen |  |  | 98 |  | 0 | [6 empty] | 2020-03-27
156 | 20200319 | ASW | GEELY_BX11_ESP9.3HD_BL06_SP01 | - | 1381575 | HMI_ApbFunctionLamp | - | - | 1381575.zip | (v2.0.147303.0) | HOU Jue (CC-AS/EVA-SW2-CN) |  | thanh.nguyen-kim |  |  | 46 |  | 0 | [6 empty] | 2020-03-27
157 | 20200319 | ASW | GEELY_BX11_ESPHEVX_BL06_SP01 | - | 1382215 | HMI_ApbFunctionLamp | - | - | 1382215.zip | (V1.3.147303.0) | ZHANG Lucy (CC-AS/EVA-SW2-CN) |  | loc.do-phu |  |  | 60 |  | 0 | [6 empty] | 2020-03-27
158
159
160
161
Table KPI ASW
No | Tester | Loc Assigned | LOC Complete | Actual Effort (days) | KPI/days | Status (%)
1 | duong.nguyen | 249 | 249 | 2.625 | 94.8571 | 100%
2 | loc.do-phu | 103 | 23 | 1.125 | 20.4444 | 22.33%
3 | thanh.nguyen-kim | 27 | 27 | 0.7875 | 34.2857 | 100%
4 | chung.ly | 0 | 0 | 0 | N/A | N/A
Total |  | 379 | 299 | 4.5375 | 65.8953 | 78.89%
Table KPI PSW
No | Tester | Loc Assigned | LOC Complete | Actual Effort (days) | KPI/days | Status (%)
1 | duong.nguyen | 4282 | 4270 | 10.8788 | 392.5083 | 99.72%
2 | loc.do-phu | 7880 | 7880 | 11.125 | 708.3146 | 100%
3 | thanh.nguyen-kim | 7412 | 7412 | 14.2625 | 519.6845 | 100%
4 | chung.ly | 8751 | 8751 | 10.675 | 819.7658 | 100%
Total |  | 28369 | 28313 | 46.9412 | 603.1582 | 99.8%
Judge Total KPI
No | Tester | Loc Assigned | LOC Complete | Actual Effort (days) | KPI/days | Status (%)
1 | duong.nguyen | 5143.9231 | 5131.9231 | 14.25 | 360.135 | 99.77%
2 | loc.do-phu | 8236.5385 | 7959.6154 | 13.25 | 600.7257 | 96.64%
3 | thanh.nguyen-kim | 7505.4615 | 7505.4615 | 13.25 | 566.4499 | 100%
4 | chung.ly | 8751 | 8751 | 14.25 | 614.1053 | 100%
Total |  | 29636.9231 | 29348 | 57 | 514.8772 | 99.03%
Note on A27: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Purple must be complete before 11-03
Note on I27: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be run Tool Auto Comment to generate header and add cmt in section "Test Goal"
Note on K69: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): \\hc-ut40745c\Ban_Vien_external\DB\05-march
Note on A74: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Yellow must be complete before 12-03 EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45):
Note on K74: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): \\hc-ut40745c\Ban_Vien_external\DB\04-march
Note on I76: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be use "Auto Comment"
Note on A89: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Orange must be complete before 13_Mar
Note on B103: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be complete before 17_Mar
Note on A118: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be complete before 18_Mar
Note on A123: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be complete before 20_Mar
Note on A133: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be complete before 25_Mar
Note on A147: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be complete before 26_Mar
Note on A153: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be complete before 27-Mar

## Report_For_Each_Project
1 | Project | 20200302
| Time | 5.8284 | days
Duration (Plan)
Duration (Actual)
| Status | Delayed
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 2557 | 2557 | 5.6822 | 7.75 | 100%
|  | 2 | ASW | 19 | 19 | 0.14615 | 0.5 | 100%
Brief Description:
2 | Project | 20200303
| Time | 17.8291 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 7850 | 7806 | 17.4444 | 13.7438 | 99.44%
|  | 2 | ASW | 50 | 50 | 0.38462 | 0.75 | 100%
Brief Description:
3 | Project | 20200304
| Time | 8.4044 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 3782 | 3770 | 8.4044 | 4.15 | 99.68%
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description:
4 | Project | 20200305
| Time | 2.5578 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 1151 | 1151 | 2.5578 | 2.4375 | 100%
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description:
5 | Project | 20200306
| Time | 1.0778 | days
Duration (Plan)
Duration (Actual)
| Status | Delayed
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 485 | 485 | 1.0778 | 1.25 | 100%
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description:
6 | Project | 20200309
| Time | 7.9844 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 3593 | 3593 | 7.9844 | 5.8562 | 100%
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description:
7 | Project | 20200313
| Time | 1.9711 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 527 | 527 | 1.1711 | 0.87875 | 100%
|  | 2 | ASW | 104 | 104 | 0.8 | 0.75 | 100%
Brief Description:
8 | Project | 20200317
| Time | 4.9421 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 2172 | 2172 | 4.8267 | 3.25 | 100%
|  | 2 | ASW | 15 | 15 | 0.11538 | 0.25 | 100%
Brief Description:
9 | Project | 20200318
| Time | 0.35111 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 158 | 158 | 0.35111 | 0.3125 | 100%
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description:
10 | Project | 20200319
| Time | 0.61538 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 0 | 0 | 0 | 0 | N/A
|  | 2 | ASW | 80 | 0 | 0.61538 | 0 | 0%
Brief Description:

## Template_Weekly_Report
Date | 2020-03-02 |  | 2020-03-20
Total Days | 15
Duration | 14.25
1. Completed ELOCs of the team from the beginning of Month (Mar) till Now:
|  | # | Types | Assigned ELOCs | Completed ELOCs | Status (%) (Completed/Assigned)
|  | 1 | PSW | 28369 | 28313 | 99.8%
|  | 2 | ASW | 379 | 299 | 78.89%
2. Completed ELOCs of each member from the beginning of Month (Mar) till Now:
|  | # | External Name | PSW ELOCs | ASW ELOCs
|  | 1 | Nguyen Tuan Duong | 4270 | 249
|  | 2 | Do Phu Loc | 7880 | 23
|  | 3 | Nguyen Kim Thanh | 7412 | 27
|  | 4 | Ly Chung | 8751 | 0
3. Risks/ Pending Issues:
|  | # | Risks/ Issues
|  | 1 | -
|  | 2 | -
|  | 3 | -
|  | 4 | -
4. Found Defects/ OPLs in Month (Mar):
|  | # | External Name | Num of OPLs | Num of Defects
|  | 1 | Nguyen Tuan Duong | 6 | 0
|  | 2 | Do Phu Loc | 4 | 0
|  | 3 | Nguyen Kim Thanh | 5 | 0
|  | 4 | Ly Chung | 7 | 0
5. Leave Plan (Mar):
|  | # | External Name | Num of Day | Detail
|  | 1 | duong.nguyen | - | -
|  | 2 | loc.do-phu | 1 | -
|  | 3 | thanh.nguyen-kim | 1 | - Day-off Fri, 20-Mar
|  | 4 | chung.ly | - | -
Note:
Productivity of each Member per Day
PSW: 450 ELOCs
ASW: 150 ELOCs
Total Productivity per Month
PSW: 450x4x20 = 36,000 ELOCs
ASW: 130x4x20 = 10,400 ELOCs

## Table
KPI Table
No\Type | ASW | PSW
1 | 130 | 450
Table Type of Testing
No | Type | Tool | Detail Output
1 | ASW | ATT | 1. Test Design (.xls) 2. Plot File (.plt) 3. ATT project 4. Coverage Log
2 | PSW | Cantata | 1. TPA file (.tpa) 2. test report (.html) 3. test report (.xml) 4. test summary (.html) 5. File Coverage Fail Reason (.xls)
Table Tester
No | Member
1 | hieu.nguyen-trung
2 | hau.nguyen-tai
3 | bang.nguyen-duy
4 | dac.luu-cong
5 | duong.nguyen
6 | loc.do-phu
7 | thanh.nguyen-kim
8 | chung.ly
Status Table
No | Status
1 | N/A |  | COEM process: test-->review test----(feedback no finding)-->generate WT----(review WT no finding)---> done task Tức là bên anh gửi UT output cho internal => Có OPL có bug => Internal review OK => Làm walkthrough => Sau đó internal review Walkthrough => Send email cho External confirm OK => Mark Done
2 | Ongoing
3 | Ready for review
4 | Ready for delivery
5 | Ready for PLC
6 | Pending for OPL
7 | Complete & Closed

## Check_List
Location
| + Location Internal Project: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project
| + Location Internal Your Output: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project\001_Prj\01_COEM\01_Output_Package
Please ensure your push correct the Package name with the TaskGroup
| + Location Internal Your Release Output: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project\001_Prj\01_COEM\02_Release_Package
| + Location for delivery to internal team: | \\hc-ut40745c\Ban_Vien_external\Release\Gen_9.3

## Weekly_16_20_Mar
Date | 2020-03-20
Total Days | 21
Duration | 14.25
1. Completed ELOCs of the team from the beginning of Month (Mar) till Now:
|  | # | Types | Assigned ELOCs | Completed ELOCs | Status (%) (Completed/Assigned)
|  | 1 | PSW | 28369 | 28313 | 99.8%
|  | 2 | ASW | 379 | 299 | 78.89%
2. Completed ELOCs of each member from the beginning of Month (Mar) till Now:
|  | # | External Name | PSW ELOCs | ASW ELOCs
|  | 1 | duong.nguyen | 4270 | 249
|  | 2 | loc.do-phu | 7880 | 23
|  | 3 | thanh.nguyen-kim | 7412 | 27
|  | 4 | chung.ly | 8751 | 0
3. Risks/ Pending Issues:
|  | # | Risks/ Issues
1
2
4. Found Defects/ OPLs in Month (Mar):
|  | # | External Name | Num of OPLs | Num of Defects
|  | 1 | duong.nguyen | 6 | 0
|  | 2 | loc.do-phu | 4 | 0
|  | 3 | thanh.nguyen-kim | 5 | 0
|  | 4 | chung.ly | 7 | 0
5. Leave Plan (Mar):
|  | # | External Name | Num of Day | Detail
|  | 1 | duong.nguyen | - | -
|  | 2 | loc.do-phu | 1 | -
|  | 3 | thanh.nguyen-kim | 1 | - Day-off Fri, 20-Mar
|  | 4 | chung.ly | - | -
Note:
Productivity of each Member per Day
PSW: 450 ELOCs
ASW: 150 ELOCs
Total Productivity per Month
PSW: 450x4x20 = 36,000 ELOCs
ASW: 130x4x20 = 10,400 ELOCs
| 1 | Package | 20200309
|  | Time | 7.9775 | days
|  | Duration |  | days
|  | Status | InAdvanced
|  |  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  |  | 1 | PSW | 3593 | 3593 | 7.9775 | 5.3563 | 100%
|  |  | 2 | ASW | 0 | 0 | 0 | 0 | 0%
| 2 | Package | 20200312
|  | Time | 13.5 | days
|  | Duration |  | days
|  | Status | InAdvanced
|  |  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  |  | 1 | PSW | 6205 | 6135 | 13.5 | 7.3125 | 98.87%
|  |  | 2 | ASW | 0 | 0 | 0 | 0 | 0%
| 3 | Package | 20200313
|  | Time | 1.1663 | days
|  | Duration |  | days
|  | Status | InAdvanced
|  |  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  |  | 1 | PSW | 527 | 527 | 1.1663 | 0.875 | 100%
|  |  | 2 | ASW | 0 | 0 | 0 | 0 | 0%

## Monthly_20200320
Date | 2020-03-02 |  | 2020-03-20
Total Days | 15
Duration | 15
1. Completed ELOCs of the team from the beginning of Month (Mar) till Now:
|  | # | Types | Assigned ELOCs | Completed ELOCs | Status (%) (Completed/Assigned)
|  | 1 | PSW | 28369 | 28313 | 99.8%
|  | 2 | ASW | 379 | 299 | 78.89%
2. Completed ELOCs of each member from the beginning of Month (Mar) till Now:
|  | # | External Name | PSW ELOCs | ASW ELOCs
|  | 1 | Nguyen Tuan Duong | 4270 | 249
|  | 2 | Do Phu Loc | 7880 | 23
|  | 3 | Nguyen Kim Thanh | 7412 | 27
|  | 4 | Ly Chung | 8751 | 0
3. Risks/ Pending Issues:
|  | # | Risks/ Issues
|  | 1 | -
|  | 2 | -
|  | 3 | -
|  | 4 | -
4. Found Defects/ OPLs in Month (Mar):
|  | # | External Name | Num of OPLs | Num of Defects
|  | 1 | Nguyen Tuan Duong | 6 | 0
|  | 2 | Do Phu Loc | 4 | 0
|  | 3 | Nguyen Kim Thanh | 5 | 0
|  | 4 | Ly Chung | 7 | 0
5. Leave Plan (Mar):
|  | # | External Name | Num of Day | Detail
|  | 1 | duong.nguyen | - | -
|  | 2 | loc.do-phu | 1 | -
|  | 3 | thanh.nguyen-kim | 1 | - Day-off Fri, 20-Mar
|  | 4 | chung.ly | - | -
Note:
Productivity of each Member per Day
PSW: 450 ELOCs
ASW: 150 ELOCs
Total Productivity per Month
PSW: 450x4x20 = 36,000 ELOCs
ASW: 130x4x20 = 10,400 ELOCs
Detail
1 | Project | 20200302
| Time | 5.8284 | days
Duration (Plan)
Duration (Actual)
| Status | Delayed
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 2557 | 2557 | 5.6822 | 7.75 | 100%
|  | 2 | ASW | 19 | 19 | 0.14615 | 0.5 | 100%
Brief Description:
2 | Project | 20200303
| Time | 17.8291 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 7850 | 7806 | 17.4444 | 13.7438 | 99.44%
|  | 2 | ASW | 50 | 50 | 0.38462 | 0.75 | 100%
Brief Description:
3 | Project | 20200304
| Time | 8.4044 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 3782 | 3782 | 8.4044 | 4.15 | 100%
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description:
4 | Project | 20200305
| Time | 2.5578 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 1151 | 1151 | 2.5578 | 2.4375 | 100%
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description:
5 | Project | 20200306
| Time | 1.0778 | days
Duration (Plan)
Duration (Actual)
| Status | Delayed
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 485 | 485 | 1.0778 | 1.25 | 100%
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description:
6 | Project | 20200309
| Time | 7.9844 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 3593 | 3305 | 7.9844 | 4.7312 | 91.98%
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description:
7 | Project | 20200313
| Time | 1.9711 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 527 | 527 | 1.1711 | 0.87875 | 100%
|  | 2 | ASW | 104 | 104 | 0.8 | 0.75 | 100%
Brief Description:
8 | Project | 20200317
| Time | 4.9421 | days
Duration (Plan)
Duration (Actual)
| Status | InAdvanced
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 2172 | 1893 | 4.8267 | 2.625 | 87.15%
|  | 2 | ASW | 15 | 15 | 0.11538 | 0.25 | 100%
Brief Description:
9 | Project | 20200318
| Time | 0 | days
Duration (Plan)
Duration (Actual)
| Status | Ontime
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 0 | 0 | 0 | 0 | N/A
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description:
10 | Project | 20200319
| Time | 0 | days
Duration (Plan)
Duration (Actual)
| Status | Ontime
|  | # | Types | Assigned ELOCs | Completed ELOCs | Effort (days) | Actual Effort (days) | Status (%) (Completed/Assigned)
|  | 1 | PSW | 0 | 0 | 0 | 0 | N/A
|  | 2 | ASW | 0 | 0 | 0 | 0 | N/A
Brief Description: