## COEM_Package_20200302
No | Package | Type | Project | ComponentName | TaskID | ItemName | Type of Comment | BB | Database | ItemRevision | Owner Contact | Task Jira | TaskGroup | Tester | PeerReviewer | Status Review | ELOC Assigned | ELOC Recheck With Tool | LOC Complete | Estimation base TOOL | Actual hour | Status | Planned Start | Planned End | Start | End | Status Result | C0 | C1 | MCDC | Reason | Remark
1 | 20200302 | PSW | GAC_220680_Carbon_A18_ESPHevx_FPA/RPA_BL03 | rb\as\gaig\prj\dsmpr\src\RBVoltageHandler\src | 1348323 | RBVoltageHandler_Suppression.c | Auto | - | GAC_ESPHevX_HADHAP_Int | - | CHEN Xiaomin (CC-AS/EVA-SW31-CN) |  | T01 | duong.nguyen | hieu.nguyen-trung | Yes | 113 | 113 | 113 | 3 | 4 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-03 | OK | 100 | 100 | 100
2 | 20200302 | PSW | MC_227282_SGMW_E200_Plus_ESPCPiGen9.3_BSS04_SP02 | rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src | 1345876 | SGMW_RBA_NDS_HBCRequest_Callout.c | Auto | bb99885 | SGMW_ESP93_Carbon_Int | - | WANG Yang (CC-AS/EVA-SW32-CN) |  | T01 | loc.do-phu | hieu.nguyen-trung | Yes | 148 | 357 | 357 | 10 | 6 | Ready for review | 2020-03-03 | 2020-03-04 | 2020-03-02 | 2020-03-02 | OK | 100 | 100 | 100 | Tool collect 148 ELOC, but the real is 357
3 | 20200302 | PSW | 241595_GAC_A27_ESP9.3CP_BL04 | rb\as\gaig\A10\dsmpr\src\RBHMI\src | 1350941 | RBHMI_LDMLamp_CNMS.c | Auto | BB81650 & BB81651 | Gac_ESP93CP_A26HD_Int | - | MIAO Huafeng (CC-AS/EVA-SW32-CN) |  | T01 | duong.nguyen | hieu.nguyen-trung | Yes | 291 | 291 | 291 | 8 | 10 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-03 | OK | 100 | 100 | 100 | Wrong extension C "RBHMI_LDMLamp_CNMS.C" | Got 1 findings
4 | 20200302 | PSW | 223331_GAC_A39_Carbon_ESP9.3HD_OBD_BL07 | rb\as\cnms_core\app\obd\ObdCyclesHandler\src | 1351929 | ObdCyclesHandler.c | Auto | bb99735 | GAC_ESP93CP_Carbon_Int | - | CHEN Xiaomin (CC-AS/EVA-SW31-CN) |  | T01 | chung.ly | hieu.nguyen-trung | Yes | 254 | 254 | 254 | 4.51 | 4 | Pending for OPL | 2020-03-02 | 2020-03-03 | 2020-03-02 | 2020-03-03 | NG | 100 | 100 | 95 | Bug (Condition is always TRUE) so can not cover MCDC. | Got 1 defect Reason: not send to internal team
5 | 20200302 | ASW | DFN_ESP_Gen9.3_532EC_244112_BSS01 | - | 1352219 | PAP_Odometry | Auto | - | 1352219 | V4.2.104.1 | QIAN Li (CC-AS/EVA-SW2-CN) |  | T01 | thanh.nguyen-kim | hieu.nguyen-trung | Yes | 19 | 19 | 19 | 1.16 | 4 | Pending for OPL | 2020-03-02 | 2020-03-03 | 2020-03-03 | 2020-03-03 | NG | 95.6 | 96 | - | Bug (Condition is always TRUE) | Got 1 findings
6 | 20200302 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1351848 | RBAPLCUST_EOLDelayCtrlOrAPBMi.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | SUN Yun (CC-AS/EVA-SW31-CN) |  | T02 | thanh.nguyen-kim | hieu.nguyen-trung | Yes | 478 | 478 | 478 | 8.49 | 14 | Ready for PLC | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-04 | NG | 99 | 99 | 100 | Bug (Condition not occur) | Got 1 findings
7 | 20200302 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | rb\as\sgmw\core\app\dcom\RBAPLCust\src\ESP | 1351848 | RBAPLCUST_RDBI_TPMS.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | SUN Yun (CC-AS/EVA-SW31-CN) |  | T02 | loc.do-phu | hieu.nguyen-trung | Yes | 286 | 59 | 59 | 1.04 | 1 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-03 | 2020-03-02 | OK | 100 | 100 | 100 | Tool collect 286 ELOC, but the real is 59
8 | 20200302 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | rb\as\sgmw\core\app\dcom\RBAPLCust\src\ESP | 1351848 | RBAPLCUST_RoutineControl_TPMSReset.c | Auto | 80504 | SGMW_ESP93_Carbon_Int | - | SUN Yun (CC-AS/EVA-SW31-CN) |  | T02 | chung.ly | hieu.nguyen-trung | Yes | 110 | 110 | 110 | 1.95 | 1.9 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100
9 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\gaig\A10\app\net\RBScl\RBSclGAC\src | 1278532 | RB_SCL_GAC_RX.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS/EVA-SW31-CN) |  | T03 | loc.do-phu | hieu.nguyen-trung | Yes | 251 | 294 | 294 | 5.22 | 6.5 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-03 | 2020-03-03 | OK | 100 | 100 | 100 | Actually ELOC = 294
10 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\gaig\A10\app\net\RBScl\RBSclGAC\src | 1278532 | RB_SCL_GAC_TX.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS/EVA-SW31-CN) |  | T03 | loc.do-phu | hieu.nguyen-trung | Yes | 101 | 101 | 101 | 1.79 | 1.5 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100
11 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\cnms_core\app\net\scl\LDMFunctions\ACC\src | 1278532 | NET_SCL_Tx_AEB.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS/EVA-SW31-CN) |  | T03 | duong.nguyen |  |  | 90 | 90 | 90 | 1.6 | 2 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | NG | 86 | 83 | 100
12 | 20200302 | PSW | GAC_Beryllium_GEN93_ESP_Mainpath_BL05 | rb\as\cnms_core\app\net\scl\LDMFunctions\APA\src | 1278532 | NET_SCL_Tx_APAInformSts.c | Auto | BB81261 | GAC_ESP93CP_Int | - | ZHANG Yu (CC-AS/EVA-SW31-CN) |  | T03 | loc.do-phu | hieu.nguyen-trung | Yes | 101 | 183 | 183 | 3.25 | 3 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100 | Actually ELOC = 183
13 | 20200303 | PSW | BYD_IPB_SW_Mainstream_BL05 | rb\as\BYD\ipb\app\net\RBScl\Scl_Callout\src | 1352115 | RBA_NDS_Complex_Callout.c | Auto | none | BYD_IPB_BL05_Int | - | GUO Sasa (CC-AS/EVA-SW3-CN) |  | T01 | chung.ly |  |  | 828 | 828 |  | 14.72 | 14 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-04 | 2020-03-06 | NG | 100 | 100 | 98 | Bug (Condition is always TRUE)
14 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\dcom\RBAPLCust\src | 1353313 | RBAPLCUST_RBDI_NVMData.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH/EAS12) |  | T01 | loc.do-phu |  |  | 371 | 371 |  | 6.59 | 3 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100 | OPL It does not impact to SW functionality.
15 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\dcom\RBAPLCust\src | 1353313 | RBAPLCUST_RDBI_PBCData.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH/EAS12) |  | T01 | loc.do-phu |  |  | 254 | 254 | 254 | 4.51 | 2 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
16 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\net\scl\Callout\src\ATMwithoutSportPlus | 1353313 | NET_ATM_Callout_GWM.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH/EAS12) |  | T01 | thanh.nguyen-kim |  |  | 395 | 395 | 395 | 7.02 | 2 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
17 | 20200303 | PSW | GWM_ESP9.3CP_RBVH_Stream_BSS04 | rb\as\gwm\core\app\net\scl\Callout\src\ATMwithSportPlus | 1353313 | NET_ATM_Callout_GWM.c | Auto | none | GWM_CP_RBVH_Stream_Int | - | Ngo Nhat Tan (RBVH/EAS12) |  | T01 | thanh.nguyen-kim |  |  | 395 | 395 | 395 | 7.02 | 3 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
18 | 20200303 | ASW | - | - | 1353762 | HDC_InvalidThrPos | Auto | - | 1353762 | V3.3.147305.2 | Nguyen Quang Vinh (RBVH/EAS15) |  | T01 | duong.nguyen |  |  | 50 | 50 | 50 | 3.07 | 3 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-06 |  |  |  |  | Have issues with database, complexity of code
19 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | 1341660 | RBAPLCUST_RDBI_AnalogData.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T02 | duong.nguyen |  |  | 77 | 77 |  | 1.36 |  | N/A |  | 2020-03-11
20 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | 1341660 | RBAPLCUST_RDBI_StatusInformation.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T02 | duong.nguyen |  |  | 44 | 44 |  | 0.78 |  | N/A |  | 2020-03-11
21 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\iBooster | 1341660 | RBAPLCUST_RoutineControl_iBoosterActuatorTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T02 | duong.nguyen |  |  | 210 | 210 |  | 3.73 |  | N/A |  | 2020-03-11
22 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_InputOutputControl.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 | duong.nguyen |  |  | 622 | 622 |  | 11.05 |  | N/A |  | 2020-03-11
23 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_InputOutputControl_GeneralFunctions.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 97 | 97 |  | 1.72 |  | N/A |  | 2020-03-11
24 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_ActuationState.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 100 | 100 |  | 1.77 |  | N/A |  | 2020-03-11
25 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_CBDS.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 8 | 8 |  | 0.14 |  | N/A |  | 2020-03-11
26 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_IOCtrlState.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 148 | 148 |  | 2.63 |  | N/A |  | 2020-03-11
27 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_IPBAssemblyMode.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 17 | 17 |  | 0.3 |  | N/A |  | 2020-03-11
28 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_PBC.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 18 | 18 |  | 0.32 |  | N/A |  | 2020-03-11
29 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_SystemData.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 | loc.do-phu |  |  | 129 | 129 | 129 | 2.29 | 3 | Ready for review |  | 2020-03-11 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
30 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_SystemSensor.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 | loc.do-phu |  |  | 164 | 196 | 196 | 3.48 | 4 | Ready for review |  | 2020-03-11 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
31 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_INSCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 | loc.do-phu |  |  | 104 | 104 |  | 1.84 | 1 | Ongoing |  | 2020-03-11 | 2020-03-06 |  | NG |  |  |  | Waiting for OPL answer.
32 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBAirMonitoring.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 | loc.do-phu |  |  | 154 | 154 |  | 2.73 |  | N/A |  | 2020-03-11
33 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBBrakeFluidChange.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 | loc.do-phu |  |  | 167 | 167 |  | 2.96 |  | N/A |  | 2020-03-11
34 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBComfortPulseCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 | loc.do-phu |  |  | 147 | 147 |  | 2.61 |  | N/A |  | 2020-03-11
35 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBDynamicTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 | loc.do-phu |  |  | 254 | 254 |  | 4.51 |  | N/A |  | 2020-03-11
36 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBEvacAndFill.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 193 | 193 |  | 3.43 |  | N/A |  | 2020-03-11
37 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBLeakageAndAirTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 204 | 204 |  | 3.62 |  | N/A |  | 2020-03-11
38 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBRepairBleed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 194 | 194 |  | 3.44 |  | N/A |  | 2020-03-11
39 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBRPSCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 141 | 141 |  | 2.5 |  | N/A |  | 2020-03-11
40 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_IPBTandemMasterCylinderTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 | thanh.nguyen-kim |  |  | 190 | 190 |  | 3.37 |  | N/A |  | 2020-03-11
41 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_SteeringAngleSensorCalibration.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 107 | 107 |  | 1.9 |  | N/A |  | 2020-03-11
42 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_WheelSpeedSensorTest.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 269 | 269 |  | 4.78 |  | N/A |  | 2020-03-11
43 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\rbcn\core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_WDBI_IPBAssemblyMode.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T03 |  |  |  | 70 | 70 |  | 1.24 |  | N/A |  | 2020-03-11
44 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_RBDI_NVMData_Common.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T04 | thanh.nguyen-kim |  |  | 204 | 204 | 204 | 3.62 | 3 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-06 |  | 100 | 100 | 100
45 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_EcuReset.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T04 | thanh.nguyen-kim |  |  | 185 | 185 | 185 | 3.28 | 3 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-06 |  | 100 | 100 | 100
46 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_GeneralFunctions.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T04 |  |  |  | 68 | 68 |  | 1.2 |  | N/A |  | 2020-03-11
47 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_NVMGeneric.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T04 |  |  |  | 150 | 150 |  | 2.66 |  | N/A |  | 2020-03-11
48 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\common | 1341660 | RBAPLCUST_RDBI_VehicleSpeed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T04 |  |  |  | 25 | 25 |  | 0.44 |  | N/A |  | 2020-03-11
49 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_EOLDelayCtrlOrAPBMi.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T05 |  |  |  | 487 | 487 |  | 8.65 |  | N/A |  | 2020-03-11
50 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RDBI_WheelSpeed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T05 | thanh.nguyen-kim |  |  | 110 | 110 | 110 | 1.95 | 2 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
51 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RoutineControl_EOLTable.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T05 |  |  |  | 167 | 167 |  | 2.96 |  | N/A |  | 2020-03-11
52 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RoutineControl_SpeedLimit.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T05 |  |  |  | 42 | 42 |  | 0.74 |  | N/A |  | 2020-03-11
53 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\ESP | 1341660 | RBAPLCUST_RoutineControl_VRShutdown.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T05 |  |  |  | 40 | 40 |  | 0.71 |  | N/A |  | 2020-03-11
54 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_WDBI_NVMData_ESP.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T06 |  |  |  | 44 | 44 |  | 0.78 |  | N/A |  | 2020-03-11
55 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RBDI_NVMData_ESP.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T06 |  |  |  | 29 | 29 |  | 0.51 |  | N/A |  | 2020-03-11
56 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RDBI_WheelSpeed.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T06 |  |  |  | 110 | 110 |  | 1.95 |  | N/A |  | 2020-03-11
57 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_RoutineControl_SpeedLimit.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T06 |  |  |  | 42 | 42 |  | 0.74 |  | N/A |  | 2020-03-11
58 | 20200303 | PSW | CNMS Super Deuterium BSS01 | rb\as\cnms_core\app\dcom\RBAPLCust\src\IPB | 1341660 | RBAPLCUST_WDBI_NVMData_ESP.c | Manual | - | CNMS_Deuterium_Int | - | LU Martin (CC-AS/ESW2-CN) |  | T06 |  |  |  | 44 | 44 |  | 0.78 |  | N/A |  | 2020-03-11
59 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_ABS_3_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | duong.nguyen | duong.nguyen | Yes | 96 | 96 | 96 | 1.7 | 1.5 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | NG | 97 | 95 | 92 | OPL is already feedback, confirm it can be ignore
60 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_APC_1_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | loc.do-phu | duong.nguyen | Yes | 28 | 28 | 28 | 0.49 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
61 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_ESP_3_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | loc.do-phu | duong.nguyen | Yes | 36 | 36 | 36 | 0.64 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
62 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_HCU_PT_10_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | chung.ly | duong.nguyen | Yes | 80 | 80 | 80 | 1.42 |  | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | NG | ? | ? | ?
63 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_HCU_PT_2_Callout.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | loc.do-phu | duong.nguyen | Yes | 33 | 33 | 33 | 0.58 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
64 | 20200306 | PSW | FAW_C105EV_ESPhev | rb\as\cnms_core\app\net\scl_callout\ | 1360296 | RBA_NDS_SystemInfo.c | Manual | 99478 | FAW_Carbon_TypeF_HevX_Int | - | HU Evan (CC-AS/EVA-SW33-CN) |  |  | thanh.nguyen-kim | duong.nguyen | Yes | 212 | 212 | 212 | 3.76 | 2 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
Table KPI ASW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | N/A | N/A
2 | hau.nguyen-tai | 0 | 0 | 0 | N/A | N/A
3 | bang.nguyen-duy | 0 | 0 | 0 | N/A | N/A
4 | dac.luu-cong | 0 | 0 | 0 | N/A | N/A
5 | duong.nguyen | 50 | 50 | 0.375 | 133.3333 | 100%
6 | loc.do-phu | 0 | 0 | 0 | N/A | N/A
7 | thanh.nguyen-kim | 19 | 19 | 0.5 | 38 | 100%
8 | chung.ly | 0 | 0 | 0 | N/A | N/A
Table KPI PSW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | N/A | N/A
2 | hau.nguyen-tai | 0 | 0 | 0 | N/A | N/A
3 | bang.nguyen-duy | 0 | 0 | 0 | N/A | N/A
4 | dac.luu-cong | 0 | 0 | 0 | N/A | N/A
5 | duong.nguyen | 1543 | 590 | 2.1875 | 269.7143 | 38.24%
6 | loc.do-phu | 2867 | 2041 | 4.125 | 494.7879 | 71.19%
7 | thanh.nguyen-kim | 2169 | 1979 | 3.625 | 545.931 | 91.24%
8 | chung.ly | 1272 | 1272 | 2.4875 | 511.3568 | 100%
Note on I21: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be run Tool Auto Comment to generate header and add cmt in section "Test Goal"

## Template
No | Package | Type | Project | ComponentName | TaskID | ItemName | ItemRevision | Task Jira | TaskGroup | Tester | LOC | LOC Complete | Estimation hour | Actual hour | Status | Planned Start | Planned End | Start | End | C0 | C1 | MCDC | Reason
1 | 1 | PSW | GAC_220680_Carbon_A18_ESPHevx_FPA/RPA_BL03 | rb\as\gaig\prj\dsmpr\src\RBVoltageHandler\src\ | 1348323 | RBVoltageHandler_Suppression.c | - | N/A |  |  | 113 |  | 2 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
2 | 1 | PSW | MC_227282_SGMW_E200_Plus_ESPCPiGen9.3_BSS04_SP02 | rb\as\sgmw\CN210S\app\net\RBScl\RBScl_SGMW\src\ | 1345876 | SGMW_RBA_NDS_HBCRequest_Callout.c | - | N/A |  |  | 148 |  | 2.63 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
3 | 1 | PSW | 241595_GAC_A27_ESP9.3CP_BL04 | rb\as\gaig\A10\dsmpr\src\RBHMI\src\ | 1350941 | RBHMI_LDMLamp_CNMS.c | - | N/A |  |  | 291 |  | 5.17 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
4 | 1 | PSW | 223331_GAC_A39_Carbon_ESP9.3HD_OBD_BL07 | rb\as\cnms_core\app\obd\ObdCyclesHandler\src\ | 1351929 | ObdCyclesHandler.c | - | N/A |  |  | 254 |  | 4.51 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
5 | 1 | ASW | DFN_ESP_Gen9.3_532EC_244112_BSS01 | - | 1351929 | PAP_Odometry | 4.2.104.1 | N/A |  |  | 19 |  | 1.16 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
6 | 2 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | RBAPLCust\src\ESP\ | 1351848 | RBAPLCUST_EOLDelayCtrlOrAPBMi.c | - | N/A |  |  | 478 |  | 8.49 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
7 | 2 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | RBAPLCust\src\ESP\ | 1351848 | RBAPLCUST_RDBI_TPMS.c | - | N/A |  |  | 286 |  | 5.08 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
8 | 2 | PSW | MC_232534_SGMW_CN202C_ESP9.3CPi_ACC_BSS04_SP02 | RBAPLCust\src\ESP\ | 1351848 | RBAPLCUST_RoutineControl_TPMSReset.c | - | N/A |  |  | 110 |  | 1.95 |  | Ongoing | 2020-03-02 | 2020-04-03 | 2020-03-02
Table KPI ASW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
3 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
5 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
6 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
7 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
9 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
10 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
3
Table KPI PSW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | duong.nguyen-tuan | 0 | 0 | 0 | #DIV/0! | #DIV/0!
3

## Table
KPI Table
No\Type | ASW | PSW
1 | 130 | 450
Table Type of Testing
No | Type | Tool | Detail Output
1 | ASW | ATT | 1. Test Design (.xls) 2. Plot File (.plt) 3. ATT project 4. Coverage Log
2 | PSW | Cantata | 1. TPA file (.tpa) 2. test report (.html) 3. test report (.xml) 4. test summary (.html) 5. File Coverage Fail Reason (.xls)
Table Tester
No | Member
1 | hieu.nguyen-trung
2 | hau.nguyen-tai
3 | bang.nguyen-duy
4 | dac.luu-cong
5 | duong.nguyen
6 | loc.do-phu
7 | thanh.nguyen-kim
8 | chung.ly
Status Table
No | Status
1 | N/A |  | COEM process: test-->review test----(feedback no finding)-->generate WT----(review WT no finding)---> done task Tức là bên anh gửi UT output cho internal => Có OPL có bug => Internal review OK => Làm walkthrough => Sau đó internal review Walkthrough => Send email cho External confirm OK => Mark Done
2 | Ongoing
3 | Ready for review
4 | Ready for delivery
5 | Ready for PLC
6 | Pending for OPL
7 | Complete & Closed

## Template_Weekly_Report
Date | 2020-02-03
Total Days | 20
1. Completed ELOCs of the team from the beginning of Month (Mar) till Now:
|  | # | Types | Assigned ELOCs | Completed ELOCs | Status (%) (Completed/Assigned)
|  | 1 | PSW | ??? | ??? | ???
|  | 2 | ASW | ??? | ??? | ???
2. Completed ELOCs of each member from the beginning of Month (Mar) till Now:
|  | # | External Name | PSW ELOCs | ASW ELOCs
|  | 1 | hieu.nguyen-trung | ??? | ???
|  | 2 | duong.nguyen-tuan | ??? | ???
3. Risks/ Pending Issues:
|  | # | Risks/ Issues
1
2
4. Found Defects/ OPLs in Month (Mar):
|  | # | Defects / OPLs
1
2
5. Leave Plan (Mar):
|  | # | External Name | Num of Day | Detail
|  | 1 | hieu.nguyen-trung | ??? | ???
|  | 2 | duong.nguyen-tuan | ??? | ???
Note:
Productivity of each Member per Day
PSW: 450 ELOCs
ASW: 150 ELOCs
Total Productivity per Month
PSW: 450x4x20 = 36,000 ELOCs
ASW: 130x4x20 = 10,400 ELOCs

## Check_List
Location
| + Location Internal Project: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project
| + Location Internal Your Output: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project\001_Prj\01_COEM\01_Output_Package
Please ensure your push correct the Package name with the TaskGroup
| + Location Internal Your Release Output: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project\001_Prj\01_COEM\02_Release_Package
| + Location for delivery to internal team: | \\hc-ut40745c\Ban_Vien_external\Release\Gen_9.3